## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Ichalabad Piped Water Supply Scheme | SM/18404 | New | Material Requisition To Resource Division |  |  | RTOR000281/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 8.88 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Ichalabad Piped Water Supply Scheme | SM/18404 | New | Material Requisition To Resource Division |  |  | RTOR000439/2023-2024 | 3848/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 15.12 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Ichalabad Piped Water Supply Scheme | SM/18404 | New | Material Requisition To Resource Division |  |  | RTOR000672/2023-2024 | 5062/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Ichalabad Piped Water Supply Scheme | SM/18404 | New | Quotation for new service connection for Ichalabad PWSS PH 1. |  |  | BILL/00230/2024-2025 | BP-2024-25-121 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 36.6 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Ichalabad Piped Water Supply Scheme | SM/18404 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ICHALABAD & HATSIMUL Piped Water Supply Scheme under Burdwan ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000423/2023-2024 | 3292/BWD | 31/07/2023 | 01/01/2026 | M/S NATIONAL CONSTRUCTION | 1617.18 | 0 | 0 | 60
6 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Ichalabad Piped Water Supply Scheme | SM/18404 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 31/10/2024 | DILIP MAHATO | 53.14 | 0 | 0 | 12
Total | [13 empty] | 1751.38 | 0 | 0