## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Bhatar | Burdwan Division | SANTOSHPUR PIPED WATER SUPPLY SCHEME | SM/18405 | New | Material Requisition To Resource Division |  |  | RTOR000283/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 22.79 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Bhatar | Burdwan Division | SANTOSHPUR PIPED WATER SUPPLY SCHEME | SM/18405 | New | Material Requisition To Resource Division |  |  | RTOR000554/2023-2024 | 4949/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 123.19 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Bhatar | Central Mechanical | SANTOSHPUR PIPED WATER SUPPLY SCHEME | SM/18405 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 31/10/2024 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Bhatar | Central Mechanical | SANTOSHPUR PIPED WATER SUPPLY SCHEME | SM/18405 | New | Quotation for new electric service connection at Santoshpur PH NO.-2 |  |  | BILL/01741/2023-2024 | BP-2023-24-260 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.91 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Bhatar | Central Mechanical | SANTOSHPUR PIPED WATER SUPPLY SCHEME | SM/18405 | New | New service connection charges for Santoshpur PWSS TW-1 |  |  | BILL/01732/2023-2024 | BP-2023-24-261 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.42 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Bhatar | Central Mechanical | SANTOSHPUR PIPED WATER SUPPLY SCHEME | SM/18405 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at SANTOSHPUR Water Supply Scheme [ Block- BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000783/2023-2024 | 4076/CMD | 29/08/2023 | 28/09/2023 | SUNRISE ENGINEERING CORPORATION | 41.68 | 0 | 0 | 60
7 | PURBA BARDHAMAN | Bhatar | Burdwan Division | SANTOSHPUR PIPED WATER SUPPLY SCHEME | SM/18405 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day. [PeriodFebruary.'2025 to April'2025] |  |  | ORD/001180/2024-2025 | 129/DSD | 29/01/2025 | 17/04/2025 | MD HASIN | 1 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Bhatar | Burdwan Division | SANTOSHPUR PIPED WATER SUPPLY SCHEME | SM/18405 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period NOV.'2024 to JAN.'2025] |  |  | ORD/000847/2024-2025 | 886/DSD | 21/10/2024 | 07/01/2025 | MD HASIN | 1 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Bhatar | Burdwan Division | SANTOSHPUR PIPED WATER SUPPLY SCHEME | SM/18405 | New | FIXING OF DISPLAY BOARD WITH M.S STRUCTURE CONTAINING SCHEME DESCRIPTION AT NASIGRAM PWSS AND OTHER SCHEMES (16 Nos) WITHIN BHATAR BLOCK UNDER BURDWAN DIVISION , PHE Dte. |  |  | ORD/001423/2024-2025 | 311/DSD | 21/02/2025 | 14/03/2025 | SHUBHRA KANTI GHOSH | 1.39 | 0 | 0 | 0
Total | [13 empty] | 284.39 | 0 | 0