## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Bara Bainan Piped Water Supply Scheme | SM/18406 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BARABAINAN & CHAUDANGA Piped Water Supply Scheme under Raina ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000412/2023-2024 | 3257/BWD | 27/07/2023 | 11/04/2026 | SK ALIM | 1144.16 | 274.36 | 23.98 | 90
2 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Bara Bainan Piped Water Supply Scheme | SM/18406 | New | Continuation Work Order supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2023 to 31-01-2024) |  |  | ORD/000985/2023-2024 | 2561/BSD | 30/10/2023 | 04/01/2024 | MD HASIN | 0.85 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Bara Bainan Piped Water Supply Scheme | SM/18406 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Barabainan Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000725/2023-2024 | 4036/CMD | 29/08/2023 | 28/09/2023 | S.K. ENTERPRISE | 28.98 | 23.16 | 79.89 | 96
4 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Bara Bainan Piped Water Supply Scheme | SM/18406 | New | Material Requisition To Resource Division |  |  | RTOR000231/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 10.15 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Bara Bainan Piped Water Supply Scheme | SM/18406 | New | Material Requisition To Resource Division |  |  | RTOR000232/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 10.15 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Bara Bainan Piped Water Supply Scheme | SM/18406 | New | Material Requisition To Resource Division |  |  | RTOR000424/2023-2024 | 3838/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 8.01 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Bara Bainan Piped Water Supply Scheme | SM/18406 | New | Quotation for new electric service connection at Bara Bainan PH NO.-1 |  |  | BILL/01742/2023-2024 | BP-2023-24-262 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.49 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Bara Bainan Piped Water Supply Scheme | SM/18406 | New | Supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-02-2024 to 30-04-2024) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001181/2023-2024 | 188/BSD | 31/01/2024 | 06/04/2024 | PARVIN BEGAM | 0.85 | 0.28 | 33.18 | 97
9 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Bara Bainan Piped Water Supply Scheme | SM/18406 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 23/12/2024 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Bara Bainan Piped Water Supply Scheme | SM/18406 | New | Installation of starter in the temporary Kisok and allied works for urgent FHTC at BOROBOINAN PUMP HOUSE NO. 2 (RAINA-02 BLOCK) W/s scheme under CMD PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000651/2024-2025 | 770/CMSD | 21/05/2024 | 31/05/2024 | S.K. ENTERPRISE | 1 | 0 | 0 | 100
11 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Bara Bainan Piped Water Supply Scheme | SM/18406 | New | Installation of starter in the temporary Kisok and allied works for urgent FHTC at BOROBOINAN PUMP HOUSE NO 1 (RAINA 02 BLOCK) w/s scheme under CMD,PHE ,Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000653/2024-2025 | 769/CMSD | 21/05/2024 | 31/05/2024 | S.K. ENTERPRISE | 1 | 0 | 0 | 100
12 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Bara Bainan Piped Water Supply Scheme | SM/18406 | New | Material Requisition To Resource Division |  |  | RTOR000788/2023-2024 | 320/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 21.17 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Bara Bainan Piped Water Supply Scheme | SM/18406 | New | New service connection charges for Bara Bainan PWSS TW-2 |  |  | BILL/02212/2023-2024 | BP-2023-24-387 | 17/01/2024 | 17/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.11 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Bara Bainan Piped Water Supply Scheme | SM/18406 | New | New Service connection at BARA BAINAN PWSS TW-1. |  |  | BILL/02361/2023-2024 | BP-2023-24-485 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.68 | 0 | 0 | 0
Total | [13 empty] | 1323 | 297.8 | 22.51