## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | HATSIMUL PIPED WATER SUPPLY SCHEME | SM/18409 | New | Material Requisition To Resource Division |  |  | RTOR000441/2023-2024 | 3846/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 17.48 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | HATSIMUL PIPED WATER SUPPLY SCHEME | SM/18409 | New | Material Requisition To Resource Division |  |  | RTOR000277/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 2.25 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | HATSIMUL PIPED WATER SUPPLY SCHEME | SM/18409 | New | Material Requisition To Resource Division |  |  | RTOR000671/2023-2024 | 5076/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | HATSIMUL PIPED WATER SUPPLY SCHEME | SM/18409 | New | Electric quotation for New Service Connection at Hatsimul W/S Scehem PH-I. |  |  | BILL/01771/2023-2024 | BP-2023-24-29 | 26/12/2023 | 26/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.13 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | HATSIMUL PIPED WATER SUPPLY SCHEME | SM/18409 | New | Electric quotation for New Service Connection at Hatsimul W/S Scehem PH-II. |  |  | BILL/01772/2023-2024 | BP-2023-24-293 | 26/12/2023 | 26/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.12 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | HATSIMUL PIPED WATER SUPPLY SCHEME | SM/18409 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 31/10/2024 | DILIP MAHATO | 53.14 | 0 | 0 | 12
7 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | HATSIMUL PIPED WATER SUPPLY SCHEME | SM/18409 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Hatsimul Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000671/2023-2024 | 4009?CMD | 29/08/2023 | 28/09/2023 | WEST BENGAL ENGINEERING CO. | 28.96 | 23.34 | 80.61 | 100
8 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | HATSIMUL PIPED WATER SUPPLY SCHEME | SM/18409 | New | Material Requisition To Resource Division |  |  | RTOR000021/2024-2025 | 303/BWD | 15/01/2025 | 15/01/2025 | Resource Division | 13.33 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | HATSIMUL PIPED WATER SUPPLY SCHEME | SM/18409 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ICHALABAD & HATSIMUL Piped Water Supply Scheme under Burdwan ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000423/2023-2024 | 3292/BWD | 31/07/2023 | 01/01/2026 | M/S NATIONAL CONSTRUCTION | 1617.18 | 268.4 | 16.6 | 60
Total | [13 empty] | 1762.04 | 291.74 | 16.56