## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL | SM/18439 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of SIMLON (ZONE-I & II) [KALNA-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/001301/2023-2024 | 259/CMD | 19/01/2024 | 18/02/2024 | DUTTA ENTERPRISE | 24.4 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL | SM/18439 | Augmentation | Illumination arrangement and miscellaneous works at Simlon water supply scheme under Kalna-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000402/2024-2025 | 2781/CMD | 01/10/2024 | 30/11/2024 | SUDIPTA GHOSH | 9.5 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL | SM/18439 | Augmentation | Laying of rising main along with crossing of pipe line by HDD/Jack pushing method due to widening of Bardhaman-Kalna Road via Simlon in connection with Augmentation of SIMLON Piped Water Supply Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000129/2024-2025 | 2070/BWD | 07/06/2024 | 05/10/2024 | MANASH GHOSH | 199.36 | 199.36 | 100 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL | SM/18439 | Augmentation | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 11 Nos. Piped W/S. Schemes under Kalna I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000335/2024-2025 | 3015/BWD | 05/08/2024 | 04/10/2024 | HORIZEN | 29.6 | 11.1 | 37.5 | 10
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL | SM/18439 | Augmentation | Quotation from WBSEDCL for Shifting of 33 KV & LTOH line at Briddhapara village against 1st T.W. of Simlon w/s scheme. |  |  | BILL/00172/2024-2025 | 270/JJM | 21/05/2024 | 21/05/2024 | WBSEDCL | 14.29 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL | SM/18439 | Augmentation | Quotation for new service connection at Simlon Zone-2 PWSS TW-1. |  |  | BILL/01190/2024-2025 | BP-2024-25-411 | 11/12/2024 | 11/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.61 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL | SM/18439 | Augmentation | AUGMENTATION OF SIMLON Piped Water Supply Scheme with sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of 500 cum capacity RCC OHRs with 20.0 mtr. Staging height including soil investigation (2 Nos.) & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site OF ZONE-I & ZONE-II under KALNA-I Block, District:- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000460/2023-2024 | 3442/BWD | 08/08/2023 | 02/04/2025 | MANASH GHOSH | 1406.99 | 980.63 | 69.7 | 60
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL | SM/18439 | Augmentation | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 07/02/2026 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
Total | [13 empty] | 2897.37 | 1191.08 | 41.11