## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KULSANA PIPE WATER SUPPLY SCHEME | SM/18440 | New | Material Requisition To Resource Division |  |  | RTOR000389/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 1.75 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KULSANA PIPE WATER SUPPLY SCHEME | SM/18440 | New | Material Requisition To Resource Division |  |  | RTOR000406/2023-2024 | 3826/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 4.47 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | KULSANA PIPE WATER SUPPLY SCHEME | SM/18440 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 25/11/2024 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KULSANA PIPE WATER SUPPLY SCHEME | SM/18440 | New | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000107/2024-2025 | 485/KTS | 16/04/2024 | 27/06/2024 | AJIT SAMANTA | 0.92 | 0.23 | 25 | 10
5 | PURBA BARDHAMAN | Mangolkote | Central Drilling | KULSANA PIPE WATER SUPPLY SCHEME | SM/18440 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilizing Departmental Machineries for Kulsana W/S Scheme (T/W-I & II), Block- Mangolkote under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000154/2023-2024 | 1341/CDD | 13/09/2023 | 31/07/2024 | SUNRISE ENGINEERING CORPORATION | 23.34 | 19.11 | 81.9 | 100
6 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KULSANA PIPE WATER SUPPLY SCHEME | SM/18440 | New | Material Requisition To Resource Division |  |  | RTOR000801/2023-2024 | 308/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 32.08 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KULSANA PIPE WATER SUPPLY SCHEME | SM/18440 | New | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 4099/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 20.51 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | KULSANA PIPE WATER SUPPLY SCHEME | SM/18440 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KULSANA PWSS TW-1 |  |  | BILL/00367/2024-2025 | BP-2024-25-187 | 08/07/2024 | 08/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.91 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | KULSANA PIPE WATER SUPPLY SCHEME | SM/18440 | New | Quotation for new service connection at Kulsana PWSS TW-2 |  |  | BILL/00376/2024-2025 | BP-2024-25-186 | 08/07/2024 | 08/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.43 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KULSANA PIPE WATER SUPPLY SCHEME | SM/18440 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHAKULIA, KULSANA & HALIMPUR Piped Water Supply Scheme under MONGALKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | J.E. katwa,JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000461/2023-2024 | 3443/BWD | 08/08/2023 | 21/11/2025 | ASHOK KUMAR GHOSH | 1588.1 | 252.57 | 15.9 | 15
11 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | KULSANA PIPE WATER SUPPLY SCHEME | SM/18440 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KULSANA Water Supply Scheme [ Block-MANGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000876/2023-2024 | 4139/CMD | 29/08/2023 | 30/05/2025 | M/S, S.S. ENTERPRISE. | 44.56 | 3.11 | 6.99 | 43
12 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KULSANA PIPE WATER SUPPLY SCHEME | SM/18440 | New | Balance work of KULSANA Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongalkote Block, District:- Purba-Bardhaman. | Assistant Engineer |  | ORD/001303/2024-2025 | 935/BWD | 11/03/2025 | 09/07/2025 | M/S GHOSH CONSTRUCTION | 249.53 | 0 | 0 | 0
Total | [13 empty] | 2039.66 | 275.03 | 13.48