## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | GUSUMBA PIPED WATER SUPPLY SCHEME | SM/18441 | New | Material Requisition To Resource Division |  |  | RTOR000271/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 13.48 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | GUSUMBA PIPED WATER SUPPLY SCHEME | SM/18441 | New | Material Requisition To Resource Division |  |  | RTOR000539/2023-2024 | 4306/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 72.67 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GUSUMBA PIPED WATER SUPPLY SCHEME | SM/18441 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at GUSUMBA Water Supply Scheme [ Block- KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000863/2023-2024 | 4130/CMD | 29/08/2023 | 28/09/2023 | S.P. CONSTRUCTION | 44.39 | 19.57 | 44.08 | 31
4 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GUSUMBA PIPED WATER SUPPLY SCHEME | SM/18441 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 31/10/2024 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | GUSUMBA PIPED WATER SUPPLY SCHEME | SM/18441 | New | Balance work of OHR, construction concrete Road, Functional Household Tap Connection, Construction of drain, Road restoration etc. for GOSUMBA PWSS, under KATWA-I Block under Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000678/2024-2025 | 3622/BWD | 03/10/2024 | 01/01/2025 | MA KANKALI ENTERPRISE | 67.86 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GUSUMBA PIPED WATER SUPPLY SCHEME | SM/18441 | New | Quotation for new service connection at Gusumba PWSS, PH-2. |  |  | BILL/00463/2024-2025 | BP-2024-25-251 | 01/08/2024 | 01/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.55 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GUSUMBA PIPED WATER SUPPLY SCHEME | SM/18441 | New | NEW SERVICE CONNECTION FOR GUSUMBA PWSS TW -1. |  |  | BILL/03098/2023-2024 | BP-2023-24-638 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.88 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GUSUMBA PIPED WATER SUPPLY SCHEME | SM/18441 | New | NEW SERVICE CONNECTION FOR GUSUMBA PWSS TW-3 |  |  | BILL/00129/2024-2025 | BP-2024-25-60 | 26/04/2024 | 26/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.93 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | GUSUMBA PIPED WATER SUPPLY SCHEME | SM/18441 | New | GUSUMBA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000427/2023-2024 | 3325/BWD | 02/08/2023 | 01/10/2025 | NATIONAL CONSTRUCTION | 766.99 | 333.72 | 43.51 | 48
Total | [13 empty] | 1036.91 | 353.28 | 34.07