## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | AURIA PIPED WATER SUPPLY SCHEME | SM/18455 | New | Material Requisition To Resource Division |  |  | RTOR000213/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 17.33 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | AURIA PIPED WATER SUPPLY SCHEME | SM/18455 | New | Material Requisition To Resource Division |  |  | RTOR000433/2023-2024 | 3853/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 64.75 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | AURIA PIPED WATER SUPPLY SCHEME | SM/18455 | New | New service connection charges for Auria PWSS TW-1 |  |  | BILL/01518/2023-2024 | BP-2023-24-188 | 09/10/2023 | 09/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.89 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | AURIA PIPED WATER SUPPLY SCHEME | SM/18455 | New | New service connection charges for Auria PWSS TW-2 |  |  | BILL/01519/2023-2024 | BP-2023-24-189 | 09/10/2023 | 09/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.77 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | AURIA PIPED WATER SUPPLY SCHEME | SM/18455 | New | New service connection charges for Auria PWSS TW-3 |  |  | BILL/01520/2023-2024 | BP-2023-24-190 | 09/10/2023 | 09/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | AURIA PIPED WATER SUPPLY SCHEME | SM/18455 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 31/10/2024 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | AURIA PIPED WATER SUPPLY SCHEME | SM/18455 | New | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000602/2024-2025 | 3106/CMD | 11/12/2024 | 09/02/2025 | S.K. ELECTRICALS | 13.6 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | AURIA PIPED WATER SUPPLY SCHEME | SM/18455 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMUL & AURIA Piped Water Supply Scheme under Katwa ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000389/2023-2024 | 3198/BWD | 24/07/2023 | 01/01/2027 | MANASH GHOSH | 1418.89 | 658.51 | 46.41 | 48
9 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | AURIA PIPED WATER SUPPLY SCHEME | SM/18455 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at AURIA Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000802/2023-2024 | 4088/CMD | 29/08/2023 | 28/09/2023 | ORIENTAL ENGINEERING CO. | 44.4 | 23.46 | 52.84 | 64
10 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | AURIA PIPED WATER SUPPLY SCHEME | SM/18455 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 2 at Augumentation of Agradip Kashipur (Babladanga) Water Supply Scheme [BLOCK- Katwa-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000544/2024-2025 | 2445/CMD | 07/08/2024 | 03/06/2025 | SUBRATA BHADRA | 11.63 | 0 | 0 | 91
11 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | AURIA PIPED WATER SUPPLY SCHEME | SM/18455 | New | Material Requisition To Resource Division |  |  | RTOR000050/2024-2025 | 330/BWD | 15/01/2025 | 15/01/2025 | Resource Division | 3.44 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | AURIA PIPED WATER SUPPLY SCHEME | SM/18455 | New | Continuation work order for Hiring of one no Diesel Motor Cab (BS-VI) including the cost of fuel . mobile & other charges for the inspection of the different projects of JJM for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. (Period:- 01/09/2025 to 28/02/2026) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000723/2025-2026 | 1907/KTS | 01/09/2025 | 01/03/2026 | HAMID SK | 1.84 | 0 | 0 | 70
Total | [13 empty] | 1640.74 | 681.98 | 41.57