## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | Material Requisition To Resource Division |  |  | RTOR000342/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 10.86 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | Material Requisition To Resource Division |  |  | RTOR000410/2023-2024 | 3870/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 6.49 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | Material Requisition To Resource Division |  |  | RTOR000641/2023-2024 | 5107/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.32 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | New service connection charges for Mejhiari PWSS TW-1 |  |  | BILL/01541/2023-2024 | BP-2023-24-211 | 01/11/2023 | 01/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.05 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | New service connection charges for Mejhiari PWSS TW-2 |  |  | BILL/01538/2023-2024 | BP-2023-24-208 | 30/10/2023 | 30/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.87 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | Supply & Delivery of Submersible Pumping Machinery, suspension clamp and tube well cover etc. for Tube well No.-2 at MEJHIARI Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte.,Dist.- Purba-Bardhaman. | Driller In-Charge |  | ORD/001624/2023-2024 | 352/DIC/BMSD(D) | 22/12/2023 | 29/12/2023 | SUBRATA BHADRA | 0.89 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 31/10/2024 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000602/2024-2025 | 3106/CMD | 11/12/2024 | 09/02/2025 | S.K. ELECTRICALS | 13.6 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | Supply & Delivery of Submersible cable and column pipes for Tube Well No No:-2 at MEJHIARI water supply scheme[ Block - KATWA -2] under CMD, PHE Dte,. Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/001630/2023-2024 | 42/DIC/BMSD(D) | 15/01/2024 | 22/01/2024 | SUBRATA BHADRA | 0.82 | 0.82 | 100 | 100
10 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | Supply & delivery of valves, starter and Installation of Submersible Pumping Machinery for Tube well No. - 2 at MEJHIARI Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte., Dist.· Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/001632/2023-2024 | 46/DIC/BMSD(D) | 19/01/2024 | 03/02/2024 | SUBRATA BHADRA | 0.68 | 0.59 | 86.45 | 100
11 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | Supply & Delivery of 3 Phase actuator operated wafer type butterfly valve for Tube well No.- 2 at MEJHIARI Water Supply Scheme [Block- KATWA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/001626/2023-2024 | 24/DIC/BMSD(D) | 05/01/2024 | 12/01/2024 | SUBRATA BHADRA | 0.98 | 0.98 | 100 | 99
12 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | Supply & Delivery of Submersible Pumping Machinery, suspension clamp and tube well cover etc. for Tube well No.-2 at MEJHIARI Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte.,Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/001690/2023-2024 | 351/DIC/BMSD(D) | 22/12/2023 | 29/12/2023 | SUBRATA BHADRA | 0.89 | 0.89 | 100 | 100
13 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | Construction of Toilet (1.8 m x 1.8 m) with sanitary arrangement under MAJHIARI PWSS(SM/18456) 2nd Tube Well Site under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-05) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001267/2024-2025 | 346/KTS | 05/03/2025 | 04/04/2025 | GHOSH CONSTRUCTION | 2.45 | 0 | 0 | 100
14 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MEJHIARI Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000509/2023-2024 | 3854/CMD | 14/08/2023 | 13/09/2023 | S.K. ELECTRICALS | 28.96 | 19.54 | 67.46 | 90
15 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MEJHIARY & KARUI Piped Water Supply Scheme under Katwa ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000421/2023-2024 | 3291/BWD | 31/07/2023 | 01/07/2025 | M/S S. CHOUDHURY | 1294.79 | 559.78 | 43.23 | 100
16 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | Material Requisition To Resource Division |  |  | RTOR000049/2024-2025 | 329/BWD | 15/01/2025 | 15/01/2025 | Resource Division | 5.77 | 0 | 0 | 0
17 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | MEJHIARI PIPED WATER SUPPLY SCHEME | SM/18456 | New | Different types of works involve in connection with implementation of Aug. Mongalkote, Palishgram, Purba Nowapara, Sitahati, Singhi, Mejhiary & Karui Piped Water Supply Scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001191/2024-2025 | 873/BWD | 06/03/2025 | 02/09/2025 | M/S S. CHOUDHURY | 588.2 | 0 | 0 | 0
Total | [13 empty] | 2039.81 | 582.6 | 28.56