## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | LAKSHIMPUR PWSS | SM/18457 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at LAKSHIMPUR Water Supply Scheme [ Block- MONGALKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000801/2023-2024 | 4087/CMD | 29/08/2023 | 30/05/2025 | ORIENTAL ENGINEERING CO. | 44.4 | 0 | 0 | 31
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | LAKSHIMPUR PWSS | SM/18457 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SIMULIA & LAKSHIMPUR Piped Water Supply Scheme under Mongalkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000694/2023-2024 | 4363/BWD | 04/10/2023 | 30/09/2025 | PUSPA ENTERPRISE | 1090.95 | 199.9 | 18.32 | 37
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | LAKSHIMPUR PWSS | SM/18457 | New | Material Requisition To Resource Division |  |  | RTOR000569/2023-2024 | 4941/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 27.49 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | LAKSHIMPUR PWSS | SM/18457 | New | Material Requisition To Resource Division |  |  | RTOR000527/2023-2024 | 4302/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 10.51 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | LAKSHIMPUR PWSS | SM/18457 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 19/05/2025 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
6 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | LAKSHIMPUR PWSS | SM/18457 | New | Material Requisition To Resource Division |  |  | RTOR000773/2023-2024 | 206/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 17.75 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | LAKSHIMPUR PWSS | SM/18457 | New | NEW SERVICE CONNECTION FOR LAKSHIMPUR PWSS TW-1 |  |  | BILL/00188/2024-2025 | BP-2024-25-89 | 15/05/2024 | 15/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.14 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | LAKSHIMPUR PWSS | SM/18457 | New | Different types of works involve in connection with implementation of Gohgram, Jabagram, Kherua, Lakshmipur & Simulia Piped Water Supply Scheme under Mongolkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001301/2024-2025 | 936/BWD | 11/03/2025 | 07/09/2025 | M/S GHOSH CONSTRUCTION | 360.68 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | LAKSHIMPUR PWSS | SM/18457 | New | Addl. Qtn for Lakshimpur T/W 1 |  |  | BILL/01669/2024-2025 | BP-2024-25-482 | 27/03/2025 | 27/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.66 | 0 | 0 | 0
Total | [13 empty] | 1613.22 | 199.9 | 12.39