## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | SIMULIA PIPE WATER SUPPLY SCHEME | SM/18459 | New | Material Requisition To Resource Division |  |  | RTOR000323/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 18.62 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | SIMULIA PIPE WATER SUPPLY SCHEME | SM/18459 | New | Material Requisition To Resource Division |  |  | RTOR000528/2023-2024 | 4303/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 4.13 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | SIMULIA PIPE WATER SUPPLY SCHEME | SM/18459 | New | Material Requisition To Resource Division |  |  | RTOR000809/2023-2024 | 307/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 32.21 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | SIMULIA PIPE WATER SUPPLY SCHEME | SM/18459 | New | New service connection charges for Shimulia PWSS TW-1 |  |  | BILL/02197/2023-2024 | BP-2023-24-376 | 16/01/2024 | 16/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.42 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | SIMULIA PIPE WATER SUPPLY SCHEME | SM/18459 | New | New service connection charges for Simulia PWSS TW-2 |  |  | BILL/02196/2023-2024 | BP-2023-24-377 | 16/01/2024 | 16/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.22 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | SIMULIA PIPE WATER SUPPLY SCHEME | SM/18459 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at SIMULIA Water Supply Scheme [ Block- MONGOLKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000796/2023-2024 | 4084/CMD | 29/08/2023 | 30/04/2025 | P.K. ENGINEERING | 41.62 | 0 | 0 | 31
7 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | SIMULIA PIPE WATER SUPPLY SCHEME | SM/18459 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SIMULIA & LAKSHIMPUR Piped Water Supply Scheme under Mongalkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000694/2023-2024 | 4363/BWD | 04/10/2023 | 30/09/2025 | PUSPA ENTERPRISE | 1090.95 | 0 | 0 | 37
8 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | SIMULIA PIPE WATER SUPPLY SCHEME | SM/18459 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 19/05/2025 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
9 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | SIMULIA PIPE WATER SUPPLY SCHEME | SM/18459 | New | Different types of works involve in connection with implementation of Gohgram, Jabagram, Kherua, Lakshmipur & Simulia Piped Water Supply Scheme under Mongolkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001301/2024-2025 | 936/BWD | 11/03/2025 | 07/09/2025 | M/S GHOSH CONSTRUCTION | 360.68 | 0 | 0 | 0
Total | [13 empty] | 1612.5 | 0 | 0