## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | Material Requisition To Resource Division |  |  | RTOR000316/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 20.46 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | Material Requisition To Resource Division |  |  | RTOR000556/2023-2024 | 4889/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 75.91 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | Material Requisition To Resource Division |  |  | RTOR000437/2023-2024 | 3850/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 63.64 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | New service connection charges for Karui PWSS TW-2 |  |  | BILL/00798/2023-2024 | BP-2023-24-86 | 26/07/2023 | 26/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.67 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | New service connection charges for Karui PWSS TW-3 |  |  | BILL/01354/2023-2024 | BP-2023-24-132 | 22/08/2023 | 22/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.65 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | New service connection charges for Karui PWSS TW-1 |  |  | BILL/00821/2023-2024 | BP-2023-24-101 | 03/08/2023 | 03/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.19 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | Continuation order for Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of The Driller In Charge, Bardhaman Mech, Sub Division ( Drilling) under C.M.D. P.H.E. Dte. w.e.f.-01/11/2023 to 31/12/2023. | Driller In-Charge | Junior Engineer | ORD/001198/2023-2024 | 159/DIC/BMSD(D) | 31/10/2023 | 31/12/2023 | SUBRATA BHADRA | 0.79 | 0 | 0 | 100
8 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of The Driller In Charge, Bardhaman Mech, Sub Division ( Drilling) under C.M.D. P.H.E. Dte. w.e.f.-01/09/2023 to 31/10/2023. | Driller In-Charge | Junior Engineer | ORD/001162/2023-2024 | 70/DIC/BMSD(D) | 28/08/2023 | 28/10/2023 | SUBRATA BHADRA | 0.79 | 0 | 0 | 100
9 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of site for the office of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte, [w.e.f: 01.07.2024 to 31.08.2024] | Driller In-Charge | Junior Engineer | ORD/000053/2024-2025 | 350/DIC/BMSD(D) | 27/06/2024 | 28/08/2024 | SUBRATA BHADRA | 0.79 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of site for the office of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte, [w.e.f.-01/05/2024 to 30/06/2024] | Driller In-Charge | Junior Engineer | ORD/000002/2024-2025 | 259/DIC/BMSD(D) | 26/04/2024 | 26/06/2024 | SUBRATA BHADRA | 0.79 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of site for the office of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte, Dte. [w.e.f: 01.01.2024 to 29.02.2024] | Driller In-Charge | Junior Engineer | ORD/001697/2023-2024 | 365/DIC/BMSD(D) | 29/12/2023 | 27/02/2024 | SUBRATA BHADRA | 0.78 | 0 | 0 | 100
12 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of site for the office of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte, [w.e.f: 01.03.2024 to 30.04.2024] | Driller In-Charge | Junior Engineer | ORD/001726/2023-2024 | 141/DIC/BMSD(D) | 29/02/2024 | 30/04/2024 | SUBRATA BHADRA | 0.79 | 0 | 0 | 100
13 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 31/10/2024 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000602/2024-2025 | 3106/CMD | 11/12/2024 | 09/02/2025 | S.K. ELECTRICALS | 13.6 | 0 | 0 | 0
15 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | Material Requisition To Resource Division |  |  | RTOR000778/2023-2024 | 326/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 8.78 | 0 | 0 | 0
16 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | Construction of Toilet (1.8 m x 1.8 m) with sanitary arrangement under KARUI PWSS (SM/18460) 3rd Tube Well Site under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-04) |  |  | ORD/001265/2024-2025 | 345/KTS | 05/03/2025 | 04/04/2025 | JAMALUDDIN SK | 2.46 | 0 | 0 | 0
17 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | Construction of Toilet (1.8 m x 1.8 m) with sanitary arrangement under KARUI PWSS (SM/18460) 2nd Tube Well Site under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-3) |  |  | ORD/001264/2024-2025 | 344/KTS | 05/03/2025 | 04/04/2025 | JAMALUDDIN SK | 2.46 | 0 | 0 | 0
18 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KARUI Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000215/2023-2024 | 3099/CMD | 24/07/2023 | 24/01/2025 | JAL PRAVAHIKA PVT LTD | 44.4 | 0 | 0 | 91
19 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | KARUI PIPED WATER SUPPLY SCHEME | SM/18460 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MEJHIARY & KARUI Piped Water Supply Scheme under Katwa ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000421/2023-2024 | 3291/BWD | 31/07/2023 | 01/07/2025 | M/S S. CHOUDHURY | 1294.79 | 0 | 0 | 100
Total | [13 empty] | 1594.92 | 0 | 0