## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | NANAGAR PIPED WATER SUPPLY SCHEME | SM/18479 | New | Material Requisition To Resource Division |  |  | RTOR000350/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 11.62 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | NANAGAR PIPED WATER SUPPLY SCHEME | SM/18479 | New | Material Requisition To Resource Division |  |  | RTOR000561/2023-2024 | 4935/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 56.21 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | NANAGAR PIPED WATER SUPPLY SCHEME | SM/18479 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at NANAGAR Water Supply Scheme [ Block- KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000878/2023-2024 | 4141/CMD | 29/08/2023 | 28/09/2023 | S.P. CONSTRUCTION | 44.39 | 0 | 0 | 30
4 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | NANAGAR PIPED WATER SUPPLY SCHEME | SM/18479 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 31/10/2024 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | NANAGAR PIPED WATER SUPPLY SCHEME | SM/18479 | New | Balance work of OHR, construction Concrete Road, Functional Household Tap Connection, Road restoration etc. for Nanagar PWSS, Srikhanda PWSS, under KATWA -I Block under Katwa Sub-Divn under Burdwan Division, PHE Dte. District:- Purba-Bardhaman. | Assistant Engineer |  | ORD/000685/2024-2025 | 3655/BWD | 21/10/2024 | 18/02/2025 | HAMID SK | 121.69 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | NANAGAR PIPED WATER SUPPLY SCHEME | SM/18479 | New | ADDITIONAL QUOTATION NEW SERVICE CONNECTION FOR NANAGAR PWSS TW -1. |  |  | BILL/03104/2023-2024 | BP-2023-24-644 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.02 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | NANAGAR PIPED WATER SUPPLY SCHEME | SM/18479 | New | NEW SERVICE CONNECTION FOR NANAGAR PWSS TW-2 |  |  | BILL/00130/2024-2025 | BP-2024-25-59 | 26/04/2024 | 26/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.11 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | NANAGAR PIPED WATER SUPPLY SCHEME | SM/18479 | New | New service connection for NANAGAR PWSS PH-1. |  |  | BILL/02285/2023-2024 | BP-2023-24-416 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.83 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | NANAGAR PIPED WATER SUPPLY SCHEME | SM/18479 | New | Second time additional quotation for Nanagar PWSS TW-1 |  |  | BILL/00665/2024-2025 | BP-2024-25-267 | 20/08/2024 | 20/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.34 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | NANAGAR PIPED WATER SUPPLY SCHEME | SM/18479 | New | NANAGAR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/000490/2023-2024 | 3507/BWD | 10/08/2023 | 01/01/2026 | GUPTA ENTERPRISE | 660.65 | 0 | 0 | 75
Total | [13 empty] | 962 | 0 | 0