## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | BANDMURA PIPED WATER SUPPLY SCHEME | SM/18480 | New | Material Requisition To Resource Division |  |  | RTOR000549/2023-2024 | 4312/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 73.01 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | BANDMURA PIPED WATER SUPPLY SCHEME | SM/18480 | New | BANDMURA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE,Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/000830/2023-2024 | 5007/BWD | 22/11/2023 | 01/01/2027 | MANASH GHOSH | 883.19 | 181.59 | 20.56 | 35
3 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME | SM/18480 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 31/10/2024 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | BANDMURA PIPED WATER SUPPLY SCHEME | SM/18480 | New | Material Requisition To Resource Division |  |  | RTOR000767/2023-2024 | 208/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 21.5 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME | SM/18480 | New | New service connection for Bandhmura PWSS PH-3. |  |  | BILL/02906/2023-2024 | BP-2023-24-615 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.32 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME | SM/18480 | New | NEW SERVICE CONNECTION FOR BANDMURA PWSS TW 1. |  |  | BILL/02490/2023-2024 | BP-2023-24-536 | 15/02/2024 | 15/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.36 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME | SM/18480 | New | Quotation for new service connection for Bandmura PWSS TW-2. |  |  | BILL/00776/2024-2025 | BP-2024-25-292 | 13/09/2024 | 13/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.03 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME | SM/18480 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at BANDMURA Water Supply Scheme [ Block- KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000869/2023-2024 | 4132/CMD | 29/08/2023 | 10/04/2025 | GLACIER ENGINEERING CO | 44.42 | 23.74 | 53.45 | 31
9 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME | SM/18480 | New | Hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte , w.e.f : 01/ 01/ 2025 to 28/02/2025 | Driller In-Charge | JUNIOR ENGINEER | ORD/000657/2024-2025 | 922/DIC/BMSD(D) | 26/12/2024 | 23/02/2025 | SUBRATA BHADRA | 0.8 | 0.74 | 92.26 | 0
10 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME | SM/18480 | New | continuation order for Hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte ,wef : 01/ 11/ 20 24 to 31/12/2024. | Driller In-Charge | Junior Engineer | ORD/000526/2024-2025 | 739/DIC/BMSD(D) | 25/10/2024 | 25/12/2024 | SUBRATA BHADRA | 0.81 | 0.78 | 96.46 | 0
11 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME | SM/18480 | New | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte , w.e.f : 01/05/2025 to 30/06/2025. | Driller In-Charge | JUNIOR ENGINEER | ORD/000009/2025-2026 | 248/DIC/BMSD(D) | 23/04/2025 | 23/06/2025 | SUBRATA BHADRA | 0.81 | 0.67 | 82.96 | 0
12 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME | SM/18480 | New | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte , w.e.f : 01/03/2025 to 30/04/2025. | Driller In-Charge | JUNIOR ENGINEER | ORD/000917/2024-2025 | 134/DIC/BMSD(D) | 24/02/2025 | 26/04/2025 | SUBRATA BHADRA | 0.81 | 0.75 | 92.09 | 0
13 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME | SM/18480 | New | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte , w.e.f : 01/07/2025 to 30/08/2025. | Driller In-Charge | JUNIOR ENGINEER | ORD/000077/2025-2026 | 476/DIC/BMSD(D) | 26/06/2025 | 26/08/2025 | SUBRATA BHADRA | 0.81 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | BANDMURA PIPED WATER SUPPLY SCHEME | SM/18480 | New | Crossing of road following Jack Push method under the command area of Bandhmura PWSS (SM/18480) of Katwa-I Block under Katwa Sub-Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000033/2025-2026 | 1288/BWD | 24/04/2025 | 24/05/2025 | MANASH GHOSH | 32.76 | 0 | 0 | 100
15 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | BANDMURA PIPED WATER SUPPLY SCHEME | SM/18480 | New | Providing of left out FHTC in different location of BANDHMURA PWSS (SM/18480) at Ganfulia Mouza in order to declare Sajal Gram, under Katwa-II Block under Katwa Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001317/2024-2025 | 983/BWD | 13/03/2025 | 01/09/2025 | MANASH GHOSH | 9.43 | 0 | 0 | 100
Total | [13 empty] | 1142.22 | 208.27 | 18.23