## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-II | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | Material Requisition To Resource Division |  |  | RTOR000421/2023-2024 | 3861/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 15.75 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina-II | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | Material Requisition To Resource Division |  |  | RTOR000248/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 15 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-II | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | Material Requisition To Resource Division |  |  | RTOR000666/2023-2024 | 5087/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-II | Central Mechanical | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 23/12/2024 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-II | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | Material Requisition To Resource Division |  |  | RTOR000011/2024-2025 | 4113/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 17.04 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina-II | Central Mechanical | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | NEW SERVICE CONNECTION FOR DIGHRA PWSS |  |  | BILL/02590/2023-2024 | BP-2023-24-556 | 20/02/2024 | 20/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.16 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina-II | Central Mechanical | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | New Service connection for Dighra W/S Scheme PH No.-I |  |  | BILL/01796/2023-2024 | BP-2023-24-322 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.03 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Raina-II | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | DIGHRA Piped Water Supply Scheme with sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of 350 cum capacity RCC OHRs with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site under RAINA-II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000485/2023-2024 | 3506/BWD | 10/08/2023 | 01/01/2026 | M/S PIONEER CONSTRUCTION | 661.73 | 273.47 | 41.33 | 75
Total | [13 empty] | 828.6 | 273.47 | 33