## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-II | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | DIGHRA Piped Water Supply Scheme with sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of 350 cum capacity RCC OHRs with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site under RAINA-II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000485/2023-2024 | 3506/BWD | 10/08/2023 | 01/01/2026 | M/S PIONEER CONSTRUCTION | 661.73 | 273.47 | 41.33 | 75
2 | PURBA BARDHAMAN | Raina-II | Central Mechanical | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at DIGHRA Water Supply Scheme [ Block- RAINA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000841/2023-2024 | 4113/CMD | 29/08/2023 | 01/06/2025 | GOENKA ENTERPRISE | 28.98 | 0 | 0 | 85
3 | PURBA BARDHAMAN | Raina-II | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | Material Requisition To Resource Division |  |  | RTOR000421/2023-2024 | 3861/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 15.75 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-II | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | Material Requisition To Resource Division |  |  | RTOR000248/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 15 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-II | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | Material Requisition To Resource Division |  |  | RTOR000666/2023-2024 | 5087/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina-II | Central Mechanical | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | New Service connection for Dighra W/S Scheme PH No.-I |  |  | BILL/01796/2023-2024 | BP-2023-24-322 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.03 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina-II | Central Mechanical | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 23/12/2024 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Raina-II | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | Material Requisition To Resource Division |  |  | RTOR000011/2024-2025 | 4113/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 17.04 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Raina-II | Central Mechanical | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | NEW SERVICE CONNECTION FOR DIGHRA PWSS |  |  | BILL/02590/2023-2024 | BP-2023-24-556 | 20/02/2024 | 20/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.16 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Raina-II | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME | SM/18482 | New | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at KONARPUR (3rd TW site) under DIGHRA Piped Water Supply Scheme under RAINA-II Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000011/2025-2026 | 1212/BWD | 21/04/2025 | 05/06/2025 | A.R. TRADERS | 13.63 | 0 | 0 | 100
Total | [13 empty] | 871.21 | 273.47 | 31.39