## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | KARAJGRAM PIPED WATER SUPPLY SCHEME | SM/18483 | New | KARAJGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS,Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE,Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/000428/2023-2024 | 3326/BWD | 02/08/2023 | 31/12/2026 | MANASH GHOSH | 533.47 | 169.36 | 31.75 | 60
2 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | KARAJGRAM PIPED WATER SUPPLY SCHEME | SM/18483 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KARAJGRAM Water Supply Scheme [ Block-KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000872/2023-2024 | 4135/CMD | 29/08/2023 | 30/04/2025 | SOUNAK ENTERPRISE | 45.53 | 0 | 0 | 66
3 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | KARAJGRAM PIPED WATER SUPPLY SCHEME | SM/18483 | New | Material Requisition To Resource Division |  |  | RTOR000313/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 13.39 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | KARAJGRAM PIPED WATER SUPPLY SCHEME | SM/18483 | New | Material Requisition To Resource Division |  |  | RTOR000505/2023-2024 | 4029/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 72.54 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | KARAJGRAM PIPED WATER SUPPLY SCHEME | SM/18483 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 31/10/2024 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | KARAJGRAM PIPED WATER SUPPLY SCHEME | SM/18483 | New | New service connection for Karajgram PWSS PH-1. |  |  | BILL/02287/2023-2024 | BP-2023-24-417 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 11.35 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | KARAJGRAM PIPED WATER SUPPLY SCHEME | SM/18483 | New | Quotation for new service connection for Kharajgram PWSS TW-3 |  |  | BILL/00341/2024-2025 | BP-2024-25-164 | 01/07/2024 | 01/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.61 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | KARAJGRAM PIPED WATER SUPPLY SCHEME | SM/18483 | New | New service connection charges for Karajgram PWSS TW-2 |  |  | BILL/01098/2024-2025 | BP-2024-25-405 | 25/11/2024 | 25/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.19 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | KARAJGRAM PIPED WATER SUPPLY SCHEME | SM/18483 | New | Crossing of road following Jack Push method under the command area of Karajgram PWSS (SM/18483) of Katwa-1 Block under Katwa Sub-Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000034/2025-2026 | 1289/BWD | 24/04/2025 | 24/05/2025 | MANASH GHOSH | 26.21 | 0 | 0 | 100
10 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | KARAJGRAM PIPED WATER SUPPLY SCHEME | SM/18483 | New | Material Requisition To Resource Division |  |  | RTOR000078/2024-2025 | 404/BWD | 17/01/2025 | 17/01/2025 | Resource Division | 4.74 | 0 | 0 | 0
Total | [13 empty] | 773.19 | 169.36 | 21.9