## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | KHAJURDIHI PIPE WATER SUPPLY SCHEME | SM/18484 | New | Material Requisition To Resource Division |  |  | RTOR000377/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 16.74 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | KHAJURDIHI PIPE WATER SUPPLY SCHEME | SM/18484 | New | Material Requisition To Resource Division |  |  | RTOR000404/2023-2024 | 3828/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 96.08 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | KHAJURDIHI PIPE WATER SUPPLY SCHEME | SM/18484 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KHAJURDIHI Water Supply Scheme [ Block- KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000879/2023-2024 | 4142/CMD | 29/08/2023 | 28/09/2023 | S.P. CONSTRUCTION | 44.39 | 0 | 0 | 45
4 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | KHAJURDIHI PIPE WATER SUPPLY SCHEME | SM/18484 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 31/10/2024 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | KHAJURDIHI PIPE WATER SUPPLY SCHEME | SM/18484 | New | New Service Connection for KHAJURDIHI PWSS PH-1. |  |  | BILL/02284/2023-2024 | BP-2023-24-418 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.8 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | KHAJURDIHI PIPE WATER SUPPLY SCHEME | SM/18484 | New | New service connection for Khajurdhi, PWSS PH-2. |  |  | BILL/02286/2023-2024 | BP-2023-24-419 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.81 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | KHAJURDIHI PIPE WATER SUPPLY SCHEME | SM/18484 | New | Addl. quotation for Khajurdihi PWSS TW-2 |  |  | BILL/00830/2024-2025 | BP-2024-25-326 | 03/10/2024 | 03/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.99 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | KHAJURDIHI PIPE WATER SUPPLY SCHEME | SM/18484 | New | KHAJURDIHI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | Assistant Engineer | Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/000497/2023-2024 | 3527/BWD | 10/08/2023 | 10/10/2025 | MONDAL ENTERPRISE | 570.77 | 0 | 0 | 75
9 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | KHAJURDIHI PIPE WATER SUPPLY SCHEME | SM/18484 | New | Different work for Khajurdihi PWSS Khajurdihi and Bera mouza with boundary wall, land development, plinth protection for pump house & OHR under KHAJURDIHI PWSS, at Katwa -I Block under Katwa Sub Division under Burdwan Division PHE Dte. | Assistant Engineer |  | ORD/001190/2024-2025 | 610/BWD | 11/02/2025 | 11/06/2025 | MONDAL ENTERPRISE | 196.33 | 0 | 0 | 0
Total | [13 empty] | 986.07 | 0 | 0