## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | GIDHGRAM PIPED WATER SUPPLY SCHEME | SM/18485 | New | Material Requisition To Resource Division |  |  | RTOR000265/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 16.31 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | GIDHGRAM PIPED WATER SUPPLY SCHEME | SM/18485 | New | Material Requisition To Resource Division |  |  | RTOR000491/2023-2024 | 4015/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 74.64 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GIDHGRAM PIPED WATER SUPPLY SCHEME | SM/18485 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 31/10/2024 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GIDHGRAM PIPED WATER SUPPLY SCHEME | SM/18485 | New | New service connection for Gidhagram PWSS PH-3 |  |  | BILL/02283/2023-2024 | BP-2023-24-420 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.9 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GIDHGRAM PIPED WATER SUPPLY SCHEME | SM/18485 | New | NEW SERVICE CONNECTION FOR GIDHGRAM PWSS TW 1 |  |  | BILL/02955/2023-2024 | BP-2023-24-635 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.48 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GIDHGRAM PIPED WATER SUPPLY SCHEME | SM/18485 | New | Quotation for new service connection at Gidhgram PWSS TW 3. |  |  | BILL/01223/2024-2025 | BP-2024-25-413 | 16/12/2024 | 16/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.54 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GIDHGRAM PIPED WATER SUPPLY SCHEME | SM/18485 | New | NEW SERVICE CONNECTION FOR GIDHGRAM PWSS TW 2. |  |  | BILL/02488/2023-2024 | BP-2023-24-534 | 15/02/2024 | 15/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.91 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | GIDHGRAM PIPED WATER SUPPLY SCHEME | SM/18485 | New | GIDHGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 500cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE,Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/000453/2023-2024 | 3431/BWD | 07/08/2023 | 01/07/2026 | POWER TOOLS & ENGINEERING | 671.42 | 310.97 | 46.32 | 31
9 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GIDHGRAM PIPED WATER SUPPLY SCHEME | SM/18485 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at GIDHGRAM Water Supply Scheme [ Block-KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000873/2023-2024 | 4136/CMD | 29/08/2023 | 25/04/2025 | M/S, S.S. ENTERPRISE. | 45.53 | 23.87 | 52.44 | 64
10 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GIDHGRAM PIPED WATER SUPPLY SCHEME | SM/18485 | New | CONTINUATION ORDER-Hiring of inspection vehicle bearing no WB41H5698 (Disel/CNG/LPG driven) for supervision of JJM works under jurisdiction of the Assistant Engineer CMSD PHE Dte .[W.E.F- 01/11/2025 TO 31/12/2025] | ASSISTANT ENGINEER | Junior Engineer | ORD/000393/2025-2026 | 1436/CMSD | 29/10/2025 | 29/12/2025 | SUBRATA BHADRA | 0.81 | 0 | 0 | 0
Total | [13 empty] | 877.69 | 334.85 | 38.15