## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-II | Burdwan Division | REAN PIPED WATER SUPPLY SCHEME | SM/18504 | New | Material Requisition To Resource Division |  |  | RTOR000273/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 12.98 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Memari-II | Burdwan Division | REAN PIPED WATER SUPPLY SCHEME | SM/18504 | New | Material Requisition To Resource Division |  |  | RTOR000689/2023-2024 | 5077/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Memari-II | Burdwan Division | REAN PIPED WATER SUPPLY SCHEME | SM/18504 | New | Material Requisition To Resource Division |  |  | RTOR000426/2023-2024 | 3859/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 13.03 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-II | Central Mechanical | REAN PIPED WATER SUPPLY SCHEME | SM/18504 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System, Internal House Wiring and compound lighting arrangement for Tube well No.- 1 & 2 at REAN Water Supply Scheme [ BLOCK- MEMARI- II] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/001602/2023-2024 | 1532/CMD | 05/03/2024 | 04/05/2024 | SUBRATA BHADRA | 28.81 | 0 | 0 | 70
5 | PURBA BARDHAMAN | Memari-II | Central Mechanical | REAN PIPED WATER SUPPLY SCHEME | SM/18504 | New | New service connection for Rean W/S scheme TW No-1 |  |  | BILL/02272/2023-2024 | BP-2023-24-421 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari-II | Central Mechanical | REAN PIPED WATER SUPPLY SCHEME | SM/18504 | New | New service connection at Rean PWSS TW -2 |  |  | BILL/02329/2023-2024 | BP-2023-24-453 | 30/01/2024 | 30/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.7 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari-II | Burdwan Division | REAN PIPED WATER SUPPLY SCHEME | SM/18504 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BIJUR & REAN Piped Water Supply Scheme under Memari ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000481/2023-2024 | 3495/BWD | 09/08/2023 | 31/03/2026 | NATIONAL CONSTRUCTION | 1175.31 | 0 | 0 | 85
8 | PURBA BARDHAMAN | Memari-II | Burdwan Division | REAN PIPED WATER SUPPLY SCHEME | SM/18504 | New | Different Types of work involved in connection with different New Schemes (05 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000003/2025-2026 | 1116/BWD | 03/04/2025 | 01/08/2025 | SOFIQUL ISLAM | 176.89 | 0 | 0 | 0
Total | [13 empty] | 1438.18 | 0 | 0