## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Manteswar | Burdwan Division | KHANDRA PIPED WATER SUPPLY SCHEME | SM/18505 | New | Material Requisition To Resource Division |  |  | RTOR000580/2023-2024 | 4894/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 36.98 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Manteswar | Burdwan Division | KHANDRA PIPED WATER SUPPLY SCHEME | SM/18505 | New | Material Requisition To Resource Division |  |  | RTOR000530/2023-2024 | 4292/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 68.65 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Manteswar | Burdwan Division | KHANDRA PIPED WATER SUPPLY SCHEME | SM/18505 | New | Material Requisition To Resource Division |  |  | RTOR000779/2023-2024 | 322/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 42.03 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Manteswar | Burdwan Division | KHANDRA PIPED WATER SUPPLY SCHEME | SM/18505 | New | Material Requisition To Resource Division |  |  | RTOR000769/2023-2024 | 205/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 19.71 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Manteswar | Central Mechanical | KHANDRA PIPED WATER SUPPLY SCHEME | SM/18505 | New | New Service connection at KHANDRA PWSS TW-1. |  |  | BILL/02366/2023-2024 | BP-2023-24-486 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Manteswar | Central Mechanical | KHANDRA PIPED WATER SUPPLY SCHEME | SM/18505 | New | New Service connection at KHANDRA PWSS TW-2. |  |  | BILL/02367/2023-2024 | BP-2023-24-487 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.6 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Manteswar | Central Mechanical | KHANDRA PIPED WATER SUPPLY SCHEME | SM/18505 | New | New service connection for Khandra PH-3 PWSS. |  |  | BILL/00087/2024-2025 | BP-2024-25-26 | 19/04/2024 | 19/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.24 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Manteswar | Central Mechanical | KHANDRA PIPED WATER SUPPLY SCHEME | SM/18505 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KHANDRA Water Supply Scheme [ Block-MONTESWAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000920/2023-2024 | 4184/CMD | 29/08/2023 | 28/09/2023 | P.K. ENGINEERING | 44.74 | 0 | 0 | 33
9 | PURBA BARDHAMAN | Manteswar | Central Mechanical | KHANDRA PIPED WATER SUPPLY SCHEME | SM/18505 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 31/10/2025 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
10 | PURBA BARDHAMAN | Manteswar | Burdwan Division | KHANDRA PIPED WATER SUPPLY SCHEME | SM/18505 | New | Quotation from WBSEDCL for Shifting of 11 KV KHANDRA FEEDER of Khandra PWSS within Durgapur Sub Division under Burdwan Division, PHE Dte. Application ID-100000127499, dt-08.01.2025 |  |  | BILL/01229/2024-2025 | 1264/JJM | 31/01/2025 | 31/01/2025 | WBSEDCL | 0.77 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Manteswar | Burdwan Division | KHANDRA PIPED WATER SUPPLY SCHEME | SM/18505 | New | KHANDRA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Monteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | J.E. 1 BURDWAN | ORD/000691/2023-2024 | 4387/BWD | 05/10/2023 | 31/03/2026 | AZAD ENTERPRISE | 631.12 | 118.38 | 18.76 | 10
Total | [13 empty] | 939.26 | 118.38 | 12.6