## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BIJUR PIPED WATER SUPPLY SCHEME | SM/18605 | New | Material Requisition To Resource Division |  |  | RTOR000261/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 3.36 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BIJUR PIPED WATER SUPPLY SCHEME | SM/18605 | New | Material Requisition To Resource Division |  |  | RTOR000658/2023-2024 | 5116/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BIJUR PIPED WATER SUPPLY SCHEME | SM/18605 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 31/10/2024 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BIJUR PIPED WATER SUPPLY SCHEME | SM/18605 | New | New service connection for BIJUR PWSS TW 2. |  |  | BILL/02441/2023-2024 | BP-2023-24-526 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.86 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BIJUR PIPED WATER SUPPLY SCHEME | SM/18605 | New | New service connection at Bijur PWSS PH-1 |  |  | BILL/02355/2023-2024 | BP-2023-24-469 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.66 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BIJUR PIPED WATER SUPPLY SCHEME | SM/18605 | New | New service connection for BIJUR PWSS TW 1. |  |  | BILL/02440/2023-2024 | BP-2023-24-527 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.7 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BIJUR PIPED WATER SUPPLY SCHEME | SM/18605 | New | New service connection at Bijur PWSS PH-2 |  |  | BILL/02353/2023-2024 | BP-2023-24-470 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.63 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BIJUR PIPED WATER SUPPLY SCHEME | SM/18605 | New | Different Types of work involved in connection with different New Schemes (05 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000003/2025-2026 | 1116/BWD | 03/04/2025 | 01/08/2025 | SOFIQUL ISLAM | 176.89 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BIJUR PIPED WATER SUPPLY SCHEME | SM/18605 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bijur Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000713/2023-2024 | 4024/CMD | 29/08/2023 | 28/09/2023 | MS DAS ELECTRIC CO | 29.4 | 23.77 | 80.86 | 95
Total | [13 empty] | 277.96 | 23.77 | 8.55