## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | BERUGRAM PIPED WATER SUPPLY SCHEME | SM/18606 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Berugram Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [3rd CALL] | ASSISTANT ENGINEER | Junior Engineer | ORD/000932/2023-2024 | 4195/CMD | 29/08/2023 | 28/09/2023 | M/S, S.DAS AND ENTERPRISE. | 29.71 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME | SM/18606 | New | Land demarcation and preparation of sketch map for Haldi, Sultanpur, Berugram & Karail Piped W/S. Scheme (New Scheme) at different Blocks under JJM under Burdwan Division, PHE Dte. | AE(HQs) | J.E. 1 BURDWAN | ORD/000756/2023-2024 | 842/AE/HQ | 01/11/2023 | 16/11/2023 | M/S S. CHOUDHURY | 0.33 | 0 | 0 | 100
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME | SM/18606 | New | Material Requisition To Resource Division |  |  | RTOR000249/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 17.09 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME | SM/18606 | New | Material Requisition To Resource Division |  |  | RTOR000523/2023-2024 | 4289/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 16.32 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME | SM/18606 | New | Material Requisition To Resource Division |  |  | RTOR000655/2023-2024 | 5114/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | BERUGRAM PIPED WATER SUPPLY SCHEME | SM/18606 | New | Quotation for new service connection at Berugram W/S Scheme PH-I. |  |  | BILL/01804/2023-2024 | BP-2023-24-323 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.94 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME | SM/18606 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BERUGRAM & SULTANPUR Piped Water Supply Scheme under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000979/2023-2024 | 092/BWD | 05/01/2024 | 31/08/2025 | SK ALIM | 1368.51 | 287.39 | 21 | 55
8 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME | SM/18606 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period NOV.'2024 to JAN.'2025] |  |  | ORD/000847/2024-2025 | 886/DSD | 21/10/2024 | 07/01/2025 | MD HASIN | 1 | 0.33 | 33.33 | 0
9 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME | SM/18606 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period AUG.'2024 to OCT.'2024] |  |  | ORD/000845/2024-2025 | 575/DSD | 19/07/2024 | 05/10/2024 | MD HASIN | 1 | 0.18 | 17.95 | 0
10 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | BERUGRAM PIPED WATER SUPPLY SCHEME | SM/18606 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 31/10/2024 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 10
11 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | BERUGRAM PIPED WATER SUPPLY SCHEME | SM/18606 | New | New Service connection for Berugram PWSS TW-2. |  |  | BILL/02333/2023-2024 | BP-2023-24-475 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.69 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME | SM/18606 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day. [PeriodFebruary.'2025 to April'2025] |  |  | ORD/001180/2024-2025 | 129/DSD | 29/01/2025 | 17/04/2025 | MD HASIN | 1 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME | SM/18606 | New | Balance work of BERUGRAM & SULTANPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001214/2024-2025 | 723/BWD | 24/02/2025 | 23/08/2025 | MD HASIN | 438.83 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME | SM/18606 | New | Continuation for Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day for the month of May'2025 |  |  | ORD/000142/2025-2026 | 660/DSD | 30/04/2025 | 31/05/2025 | MD HASIN | 0.4 | 0 | 0 | 0
15 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME | SM/18606 | New | Material Requisition To Resource Division |  |  | RTOR000048/2024-2025 | 328/BWD | 15/01/2025 | 15/01/2025 | Resource Division | 3.2 | 0 | 0 | 0
Total | [13 empty] | 1954.27 | 287.9 | 14.73