## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SULTANPUR PIPED WATER SUPPLY SCHEME | SM/18607 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sultanpur Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000707/2023-2024 | 4018/CMD | 29/08/2023 | 28/09/2023 | SUBRATA BHADRA | 28.96 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SULTANPUR PIPED WATER SUPPLY SCHEME | SM/18607 | New | Material Requisition To Resource Division |  |  | RTOR000695/2023-2024 | 5071/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SULTANPUR PIPED WATER SUPPLY SCHEME | SM/18607 | New | Material Requisition To Resource Division |  |  | RTOR000327/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 17.55 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SULTANPUR PIPED WATER SUPPLY SCHEME | SM/18607 | New | Material Requisition To Resource Division |  |  | RTOR000522/2023-2024 | 4301/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 6.53 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SULTANPUR PIPED WATER SUPPLY SCHEME | SM/18607 | New | Land demarcation and preparation of sketch map for Haldi, Sultanpur, Berugram & Karail Piped W/S. Scheme (New Scheme) at different Blocks under JJM under Burdwan Division, PHE Dte. | AE(HQs) | J.E. 1 BURDWAN | ORD/000756/2023-2024 | 842/AE/HQ | 01/11/2023 | 16/11/2023 | M/S S. CHOUDHURY | 0.33 | 0 | 0 | 100
6 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SULTANPUR PIPED WATER SUPPLY SCHEME | SM/18607 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 31/10/2024 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SULTANPUR PIPED WATER SUPPLY SCHEME | SM/18607 | New | Quotation for new service connection at SULTANPUR W/S Scheme PH-I. |  |  | BILL/01812/2023-2024 | BP-2023-24-324 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.49 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SULTANPUR PIPED WATER SUPPLY SCHEME | SM/18607 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BERUGRAM & SULTANPUR Piped Water Supply Scheme under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000979/2023-2024 | 092/BWD | 05/01/2024 | 31/08/2025 | SK ALIM | 1368.51 | 317.88 | 23.23 | 55
9 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SULTANPUR PIPED WATER SUPPLY SCHEME | SM/18607 | New | Balance work of BERUGRAM & SULTANPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001214/2024-2025 | 723/BWD | 24/02/2025 | 23/08/2025 | MD HASIN | 438.83 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SULTANPUR PIPED WATER SUPPLY SCHEME | SM/18607 | New | Electric quotation bill for NEW service connection at SULTANPUR water supply scheme, P.H No.-2 (Block-Khandaghosh) |  |  | BILL/01472/2024-2025 | BP-2024-25-441 | 18/03/2025 | 18/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.91 | 0 | 0 | 0
Total | [13 empty] | 1942.1 | 317.88 | 16.37