## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | Material Requisition To Resource Division |  |  | RTOR000264/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 4.44 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | Material Requisition To Resource Division |  |  | RTOR000429/2023-2024 | 3857/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 4.47 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | Material Requisition To Resource Division |  |  | RTOR000570/2023-2024 | 4942/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 41.11 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 31/10/2024 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-05-2024 to 31-07-2024) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000108/2024-2025 | 807/BSD | 29/04/2024 | 04/07/2024 | PARVIN BEGAM | 0.85 | 0 | 0 | 100
6 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 4117/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 18.97 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | New electric connection for Bishnupur PWSS, PH-3. |  |  | BILL/01878/2023-2024 | BP-2023-24-362 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.87 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | New service connection charges for Bishnupur PWSS TW-2 |  |  | BILL/02211/2023-2024 | BP-2023-24-404 | 17/01/2024 | 17/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.36 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | New electric connection for Bishnupur PWSS, PH-1. |  |  | BILL/01877/2023-2024 | BP-2023-24-361 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 15.08 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | BISHNUPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 500 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000451/2023-2024 | 3426/BWD | 07/08/2023 | 31/03/2026 | NATIONAL CONSTRUCTION | 870.64 | 0 | 0 | 70
11 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | Different Types of work involved in connection with different New Schemes (05 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000003/2025-2026 | 1116/BWD | 03/04/2025 | 01/08/2025 | SOFIQUL ISLAM | 176.89 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at BISHNUPUR Water Supply Scheme [ Block- MEMARI-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000791/2023-2024 | 4079/CMD | 29/08/2023 | 28/09/2023 | C.M. ENTERPRISE | 44.08 | 0 | 0 | 95
Total | [13 empty] | 1218.74 | 0 | 0