## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | Material Requisition To Resource Division |  |  | RTOR000264/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 4.44 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | Material Requisition To Resource Division |  |  | RTOR000429/2023-2024 | 3857/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 4.47 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | Material Requisition To Resource Division |  |  | RTOR000570/2023-2024 | 4942/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 41.11 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 31/10/2024 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-05-2024 to 31-07-2024) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000108/2024-2025 | 807/BSD | 29/04/2024 | 04/07/2024 | PARVIN BEGAM | 0.85 | 0.28 | 33.19 | 100
6 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 4117/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 18.97 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | New electric connection for Bishnupur PWSS, PH-3. |  |  | BILL/01878/2023-2024 | BP-2023-24-362 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.87 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | New service connection charges for Bishnupur PWSS TW-2 |  |  | BILL/02211/2023-2024 | BP-2023-24-404 | 17/01/2024 | 17/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.36 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | New electric connection for Bishnupur PWSS, PH-1. |  |  | BILL/01877/2023-2024 | BP-2023-24-361 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 15.08 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | BISHNUPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 500 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000451/2023-2024 | 3426/BWD | 07/08/2023 | 31/03/2026 | NATIONAL CONSTRUCTION | 870.64 | 726.91 | 83.49 | 70
11 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | Field level data validation of FHTC executed by Agencies on the basis of pictorial data with the objective of controlling multiple entry,improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database of BISHNUPUR Pipe Water Supply Scheme in Memari-II Block within Burdwan Sub-Division under Burdwan Division,PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000887/2024-2025 | 2670/BSD | 04/12/2024 | 03/01/2025 | TECHVISION | 1.52 | 0 | 0 | 100
12 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME | SM/18608 | New | Different Types of work involved in connection with different New Schemes (05 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000003/2025-2026 | 1116/BWD | 03/04/2025 | 01/08/2025 | SOFIQUL ISLAM | 176.89 | 0 | 0 | 0
Total | [13 empty] | 1176.18 | 727.2 | 61.83