## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-I | Central Mechanical | CHANCHAL PIPED WATER SUPPLY SCHEME | SM/18609 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at CHANCHAL Water Supply Scheme [ Block- MEMARI-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000788/2023-2024 | 4078/CMD | 29/08/2023 | 28/09/2023 | UNIVERSAL ENTERPRISES | 44.1 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Memari-I | Burdwan Division | CHANCHAL PIPED WATER SUPPLY SCHEME | SM/18609 | New | Material Requisition To Resource Division |  |  | RTOR000291/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 17.41 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Memari-I | Burdwan Division | CHANCHAL PIPED WATER SUPPLY SCHEME | SM/18609 | New | Material Requisition To Resource Division |  |  | RTOR000532/2023-2024 | 4294/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 1.69 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-I | Burdwan Division | CHANCHAL PIPED WATER SUPPLY SCHEME | SM/18609 | New | Material Requisition To Resource Division |  |  | RTOR000572/2023-2024 | 4922/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 41.11 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari-I | Central Mechanical | CHANCHAL PIPED WATER SUPPLY SCHEME | SM/18609 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 31/10/2024 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari-I | Central Mechanical | CHANCHAL PIPED WATER SUPPLY SCHEME | SM/18609 | New | New Service connection for Chanchal PWSS TW-1. |  |  | BILL/02335/2023-2024 | BP-2023-24-476 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.26 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari-I | Central Mechanical | CHANCHAL PIPED WATER SUPPLY SCHEME | SM/18609 | New | New Service connection for Chanchal PWSS TW-2. |  |  | BILL/02334/2023-2024 | BP-2023-24-477 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 14.29 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari-I | Burdwan Division | CHANCHAL PIPED WATER SUPPLY SCHEME | SM/18609 | New | Shifting of 11KV HTOH Line for construction of new OHR of Chanchal pwss under Burdwan Division, PHE Dte. [Ref ID-860319929, App ID-100000124989, dt.-10/12/2024] |  |  | BILL/01092/2024-2025 | 1172/JJM | 17/12/2024 | 17/12/2024 | WBSEDCL | 7 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari-I | Burdwan Division | CHANCHAL PIPED WATER SUPPLY SCHEME | SM/18609 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHANCHAL & NUDIPUR Piped Water Supply Scheme under Memari I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000692/2023-2024 | 4389/BWD | 05/10/2023 | 04/10/2025 | MANASH GHOSH | 1343.97 | 0 | 0 | 45
10 | PURBA BARDHAMAN | Memari-I | Burdwan Division | CHANCHAL PIPED WATER SUPPLY SCHEME | SM/18609 | New | Continuation Work Order for supply of inspection Vehicle No. WB42Y- 7403 for inspection of different JJM related (schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub Division under Burdwan Division, PHE Dte consider 96.00 Km. run per day (Period from 01-05-2025 to 31-07-2025) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000181/2025-2026 | 960/BSD | 30/04/2025 | 05/07/2025 | PARVIN BEGAM | 0.85 | 0 | 0 | 100
Total | [13 empty] | 1527.31 | 0 | 0