## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-I | Burdwan Division | SANUI PIPED WATER SUPPLY SCHEME | SM/18610 | New | SANUI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 500 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000503/2023-2024 | 3536/BWD | 10/08/2023 | 01/10/2025 | M/S ASHA CONSTRUCTION | 825.12 | 238.99 | 28.96 | 35
2 | PURBA BARDHAMAN | Memari-I | Central Mechanical | SANUI PIPED WATER SUPPLY SCHEME | SM/18610 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at SANUI Water Supply Scheme [ Block- MEMARI-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000785/2023-2024 | 4077/CMD | 29/08/2023 | 01/07/2025 | JAL PRAVAHIKA PVT LTD | 44.08 | 0 | 0 | 70
3 | PURBA BARDHAMAN | Memari-I | Burdwan Division | SANUI PIPED WATER SUPPLY SCHEME | SM/18610 | New | Material Requisition To Resource Division |  |  | RTOR000434/2023-2024 | 3852/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 13.05 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-I | Burdwan Division | SANUI PIPED WATER SUPPLY SCHEME | SM/18610 | New | Material Requisition To Resource Division |  |  | RTOR000284/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 8.15 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari-I | Burdwan Division | SANUI PIPED WATER SUPPLY SCHEME | SM/18610 | New | Material Requisition To Resource Division |  |  | RTOR000573/2023-2024 | 4943/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 41.11 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari-I | Burdwan Division | SANUI PIPED WATER SUPPLY SCHEME | SM/18610 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-06-2024 to 31-08-2024" |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000228/2024-2025 | 918/BSD | 28/05/2024 | 28/08/2024 | SK. ASFIA | 1.2 | 0.8 | 66.58 | 60
7 | PURBA BARDHAMAN | Memari-I | Central Mechanical | SANUI PIPED WATER SUPPLY SCHEME | SM/18610 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 31/10/2024 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari-I | Burdwan Division | SANUI PIPED WATER SUPPLY SCHEME | SM/18610 | New | Material Requisition To Resource Division |  |  | RTOR000017/2024-2025 | 4107/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 15.04 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari-I | Central Mechanical | SANUI PIPED WATER SUPPLY SCHEME | SM/18610 | New | New service connection for Sanui W/S Scheme. |  |  | BILL/02186/2023-2024 | BP-2023-24-380 | 16/01/2024 | 16/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 15.93 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Memari-I | Central Mechanical | SANUI PIPED WATER SUPPLY SCHEME | SM/18610 | New | New service connection for Sanui W/S Scheme. |  |  | BILL/02185/2023-2024 | BP-2023-24-381 | 16/01/2024 | 16/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.95 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Memari-I | Burdwan Division | SANUI PIPED WATER SUPPLY SCHEME | SM/18610 | New | Restoration of Conc. road, Providing leftout FHTC with extension of Pipeline, construction of Pathway, drain, repairing of Pump House at Head Work site with allied works for MAGRA, SANUI, SATGACHIA Zone-I & NARAGOHALIA PIPED WATER SUPPLY SCHEME, Block-Memari-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001192/2024-2025 | 611/BWD | 11/02/2025 | 10/08/2025 | M/S ASHA CONSTRUCTION | 354.13 | 0 | 0 | 25
12 | PURBA BARDHAMAN | Memari-I | Central Mechanical | SANUI PIPED WATER SUPPLY SCHEME | SM/18610 | New | Quotation for new service connection at Sanui PWSS TW 3. |  |  | BILL/01239/2024-2025 | BP-2024-25-422 | 09/01/2025 | 09/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 11.44 | 0 | 0 | 0
Total | [13 empty] | 1382.82 | 239.79 | 17.34