## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-I | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHANCHAL & NUDIPUR Piped Water Supply Scheme under Memari I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000692/2023-2024 | 4389/BWD | 05/10/2023 | 04/10/2025 | MANASH GHOSH | 1343.97 | 12.97 | 0.96 | 45
2 | PURBA BARDHAMAN | Memari-I | Central Mechanical | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Nudipur Water Supply Scheme [ Block- Memari-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/001092/2023-2024 | 4512/CMD | 06/10/2023 | 05/11/2023 | JAL PRAVAHIKA PVT LTD | 28.96 | 22.89 | 79.06 | 100
3 | PURBA BARDHAMAN | Memari-I | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | Material Requisition To Resource Division |  |  | RTOR000358/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 19.77 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-I | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | Material Requisition To Resource Division |  |  | RTOR000533/2023-2024 | 4295/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 3.92 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari-I | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | Material Requisition To Resource Division |  |  | RTOR000684/2023-2024 | 5057/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari-I | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-08-2024 to 31-10-2024) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000557/2024-2025 | 1500/BSD | 30/07/2024 | 04/10/2024 | PARVIN BEGAM | 0.85 | 0.28 | 33.33 | 100
7 | PURBA BARDHAMAN | Memari-I | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-12-2024 to 28-02-2025 |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001043/2024-2025 | 2636/BSD | 29/11/2024 | 27/02/2025 | SK. ASFIA | 1.2 | 0 | 0 | 60
8 | PURBA BARDHAMAN | Memari-I | Central Mechanical | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 31/10/2024 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari-I | Central Mechanical | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | New service connection at Nudipur PWSS PH-2 |  |  | BILL/02354/2023-2024 | BP-2023-24-468 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.43 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Memari-I | Central Mechanical | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | New service connection at Nudipur PWSS PH-1 |  |  | BILL/02356/2023-2024 | BP-2023-24-467 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.67 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Memari-I | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for NUDIPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001115/2024-2025 | 477/BWD | 24/01/2025 | 01/10/2025 | SHIVAM UN-EMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 64.73 | 0 | 0 | 25
Total | [13 empty] | 1549.57 | 36.15 | 2.33