## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | SupervisionandextendsupporttoNABLrecognizedWaterQualityTestingBlocklevelLaboratoryunderTheExecutiveEngineer,BurdwanDivision,PublicHealthEngineeringDirectorate,GovernmentofWestBengalbyassigningteamofcompetentresourcepersonnelwhowillbeengagedforcompletesupervisionforretainingNABLrecognitionandcompilationofpreparatoryup-to-datedocumentation,Calibrationforon-sitesurveillancebyNABL(asperNABL139)foraperiodofonemonthfromthedateofcommencement.(NameofSDL: Sankari Sub District Water Testing Laboratory under Burdwan Sadar Sub Division.) |  |  | ORD/000976/2023-2024 | 3059/BSD | 29/12/2023 | 12/02/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | SupervisionandextendsupporttoNABLrecognizedWaterQualityTestingBlocklevelLaboratoryunderTheExecutiveEngineer,BurdwanDivision,PublicHealthEngineeringDirectorate,GovernmentofWestBengalbyassigningteamofcompetentresourcepersonnelwhowillbeengagedforcompletesupervisionforretainingNABLrecognitionandcompilationofpreparatoryup-to-datedocumentation,Calibrationforon-sitesurveillancebyNABL(asperNABL139)foraperiodofonemonthfromthedateofcommencement.(NameofSDL:Sehera Sub District Water Testing Laboratory under Burdwan Sadar Sub Division |  |  | ORD/000977/2023-2024 | 3060/BSD | 29/12/2023 | 12/02/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.51 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work order for Annual Maintenance Contract (AMC) for software upgradation and other software related issues in existing computers, refilling of Cartridge of the printers, replacement of battery of UPS in District, Sub-Dist. and NGO Laboratories under Burdwan Division, P.H.E. Dte. [Period from 01.02.2024 to 31.07.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/001018/2023-2024 | 46/AE/HQ | 29/01/2024 | 27/07/2024 | COMPUTER MEDIA | 0.99 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Repair & renovation of Barsul Sub District Water Testing Laboratory under Burdwan Division, P.H.E. Dte. |  | J.E. 1 BURDWAN | ORD/001068/2023-2024 | 1018/AE/HQ | 28/12/2023 | 27/01/2024 | PRATIVA CONSTRUCTION | 4.24 | 2.06 | 48.64 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Installation of Aquaguard purifier at Four nos Laboratories (SDWTL) (Dr. ChatterjeeVWS,Aikyatan,Shastri Smriti Sangha,Barshul) under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001088/2023-2024 | 98/RWS | 13/03/2024 | 28/03/2024 | KHUSI BHAKAT | 0.88 | 0.32 | 36.9 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Installation of Aquaguard purifier at District Laboratory with meeting hall at Nababhat P.H.E. Complex within RWS Burdwan Sub-Division, under Burdwan Division. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001176/2023-2024 | 05/RWS | 05/01/2024 | 12/01/2024 | KHUSI BHAKAT | 0.21 | 0.2 | 98.57 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Estimate for Operational charges and supply of different office articles of Burdwan District Laboratory under Burdwan Division, PHE Dte. (Period from 01.04.2024 to 31.03.2025 ) |  | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000082/2024-2025 | 122/RWS | 01/04/2024 | 01/04/2025 | ALAKA GHOSH | 0.99 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary payment for the month of March'2024. |  |  | BILL/00189/2024-2025 | 293/JJM | 29/05/2024 |  | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary payment for the month of March'2024. |  |  | BILL/00190/2024-2025 | 294/JJM | 29/05/2024 |  | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary payment for the month of March'2024. |  |  | BILL/00191/2024-2025 | 295/JJM | 29/05/2024 |  | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary Bill for the month of April-2024 |  |  | BILL/00259/2024-2025 | 371/JJM | 21/06/2024 |  | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | null
12 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Remuneration of Laboratory Personal for the month April-2024 |  |  | BILL/00261/2024-2025 | 370/JJM | 21/06/2024 |  | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | null
13 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Grant the Remuneration of lab staff for the month of April-2024. |  |  | BILL/00263/2024-2025 | 369/JJM | 21/06/2024 |  | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | null
14 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 3 Nos. Sub District Laboratories within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.03.2024 to 31.05.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/001153/2023-2024 | 812/BWD | 27/02/2024 | 27/05/2024 | DULAL MAJUMDER | 5.3 | 4.33 | 81.69 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | SALARY BILL FOR THE MONTH OF MAY-2024' |  |  | BILL/00260/2024-2025 | 461/JJM | 02/07/2024 |  | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | null
16 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | SALARY BILL FOR THE MONTH OF MAY-2024. |  |  | BILL/00264/2024-2025 | 460/JJM | 02/07/2024 |  | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | null
17 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | SALARY BILL FOR THE MONTH OF MAY-2024' |  |  | BILL/00262/2024-2025 | 459/JJM | 02/07/2024 |  | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | null
18 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Laboratory contingency charges bill [Period January'22 to June'22] |  |  | BILL/00282/2024-2025 | 446/JJM | 02/07/2024 |  | SIDHU KANU GRAM UNNAYAN SAMITY | 0.4 | 0 | 0 | 0
19 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Laboratory contingency charges bill [Period January'22 to June'22] |  |  | BILL/00282/2024-2025 | 446/JJM | 02/07/2024 |  | SIDHU KANU GRAM UNNAYAN SAMITY | 0.4 | 0 | 0 | 0
20 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 2 Nos. Sub District Laboratories within Burdwan Sadar Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.03.2024 to 31.05.2024] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001156/2023-2024 | 830/BWD | 28/02/2024 | 28/05/2024 | DULAL MAJUMDER | 2.99 | 2.99 | 99.9 | 100
21 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Sampling Assistant) in Bananabagram Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period for 01.03.2024 to 31.05.2024]. | AE(HQs) | J.E. 1 BURDWAN | ORD/001158/2023-2024 | 145/AE/HQ | 28/02/2024 | 28/05/2024 | DULAL MAJUMDER | 0.37 | 0.37 | 100 | 100
22 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 4 Nos. Sub District Laboratories within Kalna Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.03.2024 to 31.05.2024] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001157/2023-2024 | 858/BWD | 29/02/2024 | 29/05/2024 | DULAL MAJUMDER | 7.59 | 5.31 | 70 | 50
23 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Installation of Aquaguard purifier at 03 (Three) nos Laboratories (SDWTL) (Sehara, Sankari, Anukhal) under Burdwan Division, PHE Dte. |  | Contractual Junior Engineer | ORD/000250/2024-2025 | 192/RWS | 18/06/2024 | 25/06/2024 | GHOSH ENTERPRISE | 0.72 | 0.36 | 49.62 | 100
24 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Supply of Residual Chlorine Kit and engagement of Laboratory personnel (Chemist/Bacteriologist/ Lab Assistant and Sampling Assistant) including maintenance in 3 Nos. Sub District Laboratories within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period For Twelve Months] i.e. period from 01.08.2024 to 31.07.2025. | AE(HQs) |  | ORD/000369/2024-2025 | 2961/BWD | 31/07/2024 | 31/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 29.46 | 0 | 0 | 0
25 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Supply of Residual Chlorine Kit and engagement of Laboratory personnel (Chemist/Bacteriologist/ Lab Assistant and Sampling Assistant) including maintenance in 1 No. Sub District Laboratory within Durgapur sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period For Twelve Months] i.e. period from 01.08.2024 to 31.07.2025. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000371/2024-2025 | 2963/BWD | 31/07/2024 | 31/07/2025 | DULAL MAJUMDER | 10.49 | 0 | 0 | 0
26 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Supply of Residual Chlorine Kit and engagement of Laboratory personnel (Chemist/Bacteriologist/ Lab Assistant and Sampling Assistant) including maintenance in 2 Nos. Sub District Laboratories within Burdwan Sadar Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period For Twelve Months] i.e. period from 01.08.2024 to 31.07.2025. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000370/2024-2025 | 2962/BWD | 31/07/2024 | 31/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 19.04 | 0 | 0 | 0
27 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Installation of Aquaguard purifier at 03 (Three) nos Laboratories (SDWTL) (Satgachia, Monteswar, Parulia) under Burdwan Division, PHE Dte. |  | Contractual Junior Engineer | ORD/000253/2024-2025 | 193/RWS | 18/06/2024 | 25/06/2024 | DAS ENTERPRISE | 0.72 | 0.72 | 99.32 | 100
28 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Installation of Aquaguard purifier at 03 (Three) nos Laboratories (SDWTL) (Saktigarh, Ganganandapur, Bonnobogram) under Burdwan Division, PHE Dte. |  | Contractual Junior Engineer | ORD/000254/2024-2025 | 194/RWS | 18/06/2024 | 25/06/2024 | KHUSI BHAKAT | 0.73 | 0.73 | 99.48 | 100
29 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Supply of Materials required for maintaining NABL Accreditation as per ISO:I 17025:2017 of Bardhaman District water testing Laboratory, PHED, Govt of West Bengal. |  | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000081/2024-2025 | 151/RWS | 26/04/2024 | 03/05/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.79 | 0.39 | 49.55 | 100
30 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Sampling Assistant) in Bananabagram Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period for 01.06.2024 to 31.07.2024]. |  | J.E. 1 BURDWAN | ORD/000430/2024-2025 | 303/AE/HQ | 31/05/2024 | 30/07/2024 | DULAL MAJUMDER | 0.3 | 0 | 0 | 0
31 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 2 Nos. Sub District Laboratories within Burdwan Sadar Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.06.2024 to 31.07.2024] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000432/2024-2025 | 1981/BWD | 28/05/2024 | 27/07/2024 | DULAL MAJUMDER | 1.98 | 0 | 0 | 0
32 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 3 Nos. Sub District Laboratories within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.06.2024 to 31.07.2024] |  | J.E. 1 BURDWAN | ORD/000431/2024-2025 | 1980/BWD | 29/05/2024 | 28/07/2024 | DULAL MAJUMDER | 3.56 | 0 | 0 | 0
33 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 4 Nos. Sub District Laboratories within Kalna Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.06.2024 to 31.07.2024] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000433/2024-2025 | 2007/BWD | 30/05/2024 | 29/07/2024 | DULAL MAJUMDER | 5.04 | 2.52 | 49.99 | 0
34 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 3 Nos Water Testing Laboratories under Burdwan Division, PHE Dte. [Period: For One Month (01.07.24 to 31.07.24)] |  | J.E. 1 BURDWAN | ORD/000476/2024-2025 | 374/AE/HQ | 01/07/2024 | 01/08/2024 | DULAL MAJUMDER | 0.87 | 0 | 0 | 0
35 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 4 Nos Water Testing Laboratories under Burdwan Division, PHE Dte [Period:One Month (01.07.24 to 31.07.24)] |  | J.E. 1 BURDWAN | ORD/000475/2024-2025 | 373/AE/HQ | 01/07/2024 | 01/08/2024 | DULAL MAJUMDER | 0.87 | 0 | 0 | 0
36 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation Work Order for Engagement of 1 No. Laboratory Assistant at Bonnabagram Water Testing Laboratories under Burdwan Division, PHE Dte [Period: For Four Months (01.07.24 to 31.07.24)] |  | J.E. 1 BURDWAN | ORD/000477/2024-2025 | 375/AE/HQ | 01/07/2024 | 01/08/2024 | DULAL MAJUMDER | 0.16 | 0 | 0 | 0
37 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Supply of Residual Chlorine Kit and engagement of Laboratory personnel (Chemist/Bacteriologist/ Lab Assistant and Sampling Assistant) including maintenance in 4 Nos. Sub District Laboratories within Kalna Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period For Twelve Months] i.e. period from 01.08.2024 to 31.07.2025. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000372/2024-2025 | 2964/BWD | 31/07/2024 | 31/07/2025 | DULAL MAJUMDER | 40.12 | 0 | 0 | 2
38 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Supply of Inverter Battery, MS Rack, office table and Plastic Chair for 14 Nos. laboratory under Burdwan Division, PHE. Dte. | AE(HQs) | J.E. 1 BURDWAN | ORD/001033/2023-2024 | 102/AE/HQ | 19/02/2024 | 20/03/2024 | SANDIPAN SENGUPTA | 8.79 | 2.2 | 24.97 | 20
39 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Remuneration of lab personnel for the month of June 2024. |  |  | BILL/00556/2024-2025 | 747/JJM | 29/08/2024 |  | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | null
40 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary bill for the month of June 2024 |  |  | BILL/00557/2024-2025 | 748/JJM | 29/08/2024 |  | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | null
41 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Grant The Remuneration of Lab Staff for Month of June- 2024 |  |  | BILL/00558/2024-2025 | 749/JJM | 29/08/2024 |  | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | null
42 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 4 Nos Water Testing Laboratories under Burdwan Division, PHE Dte [Period:One Month (01.04.24 to 30.04.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/001216/2023-2024 | 234/AE/HQ | 28/03/2024 | 27/04/2024 | DULAL MAJUMDER | 0.87 | 0.87 | 100 | 100
43 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Engagement of 1 No. Laboratory Assistant at Bonnabagram Water Testing Laboratories under Burdwan Division, PHE Dte [Period: For Four Months (01.03.24 to 30.06.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/001223/2023-2024 | 131/AE/HQ | 27/02/2024 | 26/06/2024 | DULAL MAJUMDER | 0.63 | 0.63 | 100 | 100
44 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Engagement of 4 Nos Laboratory personnel (Analyst) at 3 Nos Water Testing Laboratories under Burdwan Division, PHE Dte. [Period: For One Month (01.03.24 to 31.03.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/001215/2023-2024 | 134/AE/HQ | 28/02/2024 | 30/03/2024 | DULAL MAJUMDER | 0.87 | 0.87 | 100 | 100
45 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 3 Nos Water Testing Laboratories under Burdwan Division, PHE Dte. [Period: For One Month (01.04.24 to 30.04.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/001217/2023-2024 | 235/AE/HQ | 28/03/2024 | 27/04/2024 | DULAL MAJUMDER | 0.87 | 0.75 | 86.36 | 100
46 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Monthly remuneration of lab personnel for the month of July 2024 |  |  | BILL/00567/2024-2025 | 757/JJM | 30/08/2024 |  | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | null
47 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Grant the remuneration of lab staff for the month of July 2024 |  |  | BILL/00566/2024-2025 | 757/JJM | 30/08/2024 |  | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | null
48 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary bill for the month of July 2024 |  |  | BILL/00568/2024-2025 | 757/JJM | 30/08/2024 |  | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | null
49 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Engagement of 4 Nos Laboratory personnel (Analyst) at 4 Nos Water Testing Laboratories under Burdwan Division, PHE Dte [Period: One Month (01.03.24 to 31.03.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/001214/2023-2024 | 133/AE/HQ | 28/02/2024 | 30/03/2024 | DULAL MAJUMDER | 0.87 | 0.43 | 49.99 | 100
50 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 3 Nos Water Testing Laboratories under Burdwan Division, PHE Dte. [Period: For One Month (01.06.24 to 30.06.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/000112/2024-2025 | 299/AE/HQ | 30/05/2024 | 29/06/2024 | DULAL MAJUMDER | 0.87 | 0.87 | 100 | 100
51 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 4 Nos Water Testing Laboratories under Burdwan Division, PHE Dte [Period:One Month (01.05.24 to 31.05.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/000109/2024-2025 | 275/AE/HQ | 30/04/2024 | 31/05/2024 | DULAL MAJUMDER | 0.87 | 0.87 | 100 | 100
52 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 4 Nos Water Testing Laboratories under Burdwan Division, PHE Dte [Period:One Month (01.06.24 to 30.06.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/000111/2024-2025 | 298/AE/HQ | 30/05/2024 | 29/06/2024 | DULAL MAJUMDER | 0.87 | 0.87 | 100 | 100
53 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 3 Nos Water Testing Laboratories under Burdwan Division, PHE Dte. [Period: For One Month (01.05.24 to 31.05.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/000110/2024-2025 | 276/AE/HQ | 30/04/2024 | 31/05/2024 | DULAL MAJUMDER | 0.87 | 0.87 | 100 | 100
Total | [13 empty] | 163.71 | 29.5 | 18.02