## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Supply of Inverter Battery, MS Rack, office table and Plastic Chair for 14 Nos. laboratory under Burdwan Division, PHE. Dte. | AE(HQs) | J.E. 1 BURDWAN | ORD/001033/2023-2024 | 102/AE/HQ | 19/02/2024 | 20/03/2024 | SANDIPAN SENGUPTA | 8.79 | 0 | 0 | 20
2 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work order for Annual Maintenance Contract (AMC) for software upgradation and other software related issues in existing computers, refilling of Cartridge of the printers, replacement of battery of UPS in District, Sub-Dist. and NGO Laboratories under Burdwan Division, P.H.E. Dte. [Period from 01.02.2024 to 31.07.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/001018/2023-2024 | 46/AE/HQ | 29/01/2024 | 29/07/2024 | COMPUTER MEDIA | 0.99 | 0 | 0 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Engagement of 4 Nos Laboratory personnel (Analyst) at 4 Nos Water Testing Laboratories under Burdwan Division, PHE Dte [Period: One Month (01.03.24 to 31.03.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/001214/2023-2024 | 133/AE/HQ | 28/02/2024 | 30/03/2024 | DULAL MAJUMDER | 0.87 | 0 | 0 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 4 Nos Water Testing Laboratories under Burdwan Division, PHE Dte [Period:One Month (01.04.24 to 30.04.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/001216/2023-2024 | 234/AE/HQ | 28/03/2024 | 27/04/2024 | DULAL MAJUMDER | 0.87 | 0 | 0 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 4 Nos. Sub District Laboratories within Kalna Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.06.2024 to 31.07.2024] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000433/2024-2025 | 2007/BWD | 30/05/2024 | 30/07/2024 | DULAL MAJUMDER | 5.04 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Installation of Aquaguard purifier at 03 (Three) nos Laboratories (SDWTL) (Satgachia, Monteswar, Parulia) under Burdwan Division, PHE Dte. |  | Contractual Junior Engineer | ORD/000253/2024-2025 | 193/RWS | 18/06/2024 | 25/06/2024 | DAS ENTERPRISE | 0.72 | 0 | 0 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Installation of Aquaguard purifier at 03 (Three) nos Laboratories (SDWTL) (Saktigarh, Ganganandapur, Bonnobogram) under Burdwan Division, PHE Dte. |  | Contractual Junior Engineer | ORD/000254/2024-2025 | 194/RWS | 18/06/2024 | 25/06/2024 | KHUSI BHAKAT | 0.73 | 0 | 0 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Engagement of 1 No. Laboratory Assistant at Bonnabagram Water Testing Laboratories under Burdwan Division, PHE Dte [Period: For Four Months (01.03.24 to 30.06.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/001223/2023-2024 | 131/AE/HQ | 27/02/2024 | 27/06/2024 | DULAL MAJUMDER | 0.63 | 0 | 0 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 3 Nos Water Testing Laboratories under Burdwan Division, PHE Dte. [Period: For One Month (01.06.24 to 30.06.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/000112/2024-2025 | 299/AE/HQ | 30/05/2024 | 29/06/2024 | DULAL MAJUMDER | 0.87 | 0 | 0 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of laboratory personnels i.e. Chemist (One Person), Additional Chemist (One person), Bacteriologist (One Person), Laboratory Assistant (One Person), Sampling Assistant (One Person) and Computer Operator/Data Entry Operator (One Person) for Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman. [Period for 6 (Six) Months i.e. 01.06.2024 to 30.11.2024] | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Contractual Junior Engineer | ORD/000577/2024-2025 | 1997/BWD | 30/05/2024 | 30/11/2024 | ALAKA GHOSH | 7.67 | 0 | 0 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Installation of Aquaguard purifier at 03 (Three) nos Laboratories (SDWTL) (Sehara, Sankari, Anukhal) under Burdwan Division, PHE Dte. |  | Contractual Junior Engineer | ORD/000250/2024-2025 | 192/RWS | 18/06/2024 | 25/06/2024 | GHOSH ENTERPRISE | 0.72 | 0 | 0 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Engagement of 4 Nos Laboratory personnel (Analyst) at 3 Nos Water Testing Laboratories under Burdwan Division, PHE Dte. [Period: For One Month (01.03.24 to 31.03.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/001215/2023-2024 | 134/AE/HQ | 28/02/2024 | 30/03/2024 | DULAL MAJUMDER | 0.87 | 0 | 0 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 4 Nos Water Testing Laboratories under Burdwan Division, PHE Dte [Period:One Month (01.05.24 to 31.05.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/000109/2024-2025 | 275/AE/HQ | 30/04/2024 | 31/05/2024 | DULAL MAJUMDER | 0.87 | 0 | 0 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Repair & renovation of Barsul Sub District Water Testing Laboratory under Burdwan Division, P.H.E. Dte. |  | J.E. 1 BURDWAN | ORD/001068/2023-2024 | 1018/AE/HQ | 28/12/2023 | 27/01/2024 | PRATIVA CONSTRUCTION | 4.24 | 0 | 0 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Installation of Aquaguard purifier at Four nos Laboratories (SDWTL) (Dr. ChatterjeeVWS,Aikyatan,Shastri Smriti Sangha,Barshul) under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001088/2023-2024 | 98/RWS | 13/03/2024 | 28/03/2024 | KHUSI BHAKAT | 0.88 | 0 | 0 | 100
16 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 3 Nos. Sub District Laboratories within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.03.2024 to 31.05.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/001153/2023-2024 | 812/BWD | 27/02/2024 | 27/05/2024 | DULAL MAJUMDER | 5.3 | 0 | 0 | 100
17 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 2 Nos. Sub District Laboratories within Burdwan Sadar Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.03.2024 to 31.05.2024] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001156/2023-2024 | 830/BWD | 28/02/2024 | 28/05/2024 | DULAL MAJUMDER | 2.99 | 0 | 0 | 100
18 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 4 Nos. Sub District Laboratories within Kalna Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.03.2024 to 31.05.2024] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001157/2023-2024 | 858/BWD | 29/02/2024 | 31/05/2024 | DULAL MAJUMDER | 7.59 | 0 | 0 | 50
19 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Sampling Assistant) in Bananabagram Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period for 01.03.2024 to 31.05.2024]. | AE(HQs) | J.E. 1 BURDWAN | ORD/001158/2023-2024 | 145/AE/HQ | 28/02/2024 | 28/05/2024 | DULAL MAJUMDER | 0.37 | 0 | 0 | 100
20 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Supply of Materials required for maintaining NABL Accreditation as per ISO:I 17025:2017 of Bardhaman District water testing Laboratory, PHED, Govt of West Bengal. |  | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000081/2024-2025 | 151/RWS | 26/04/2024 | 03/05/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.79 | 0 | 0 | 100
21 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Installation of Aquaguard purifier at District Laboratory with meeting hall at Nababhat P.H.E. Complex within RWS Burdwan Sub-Division, under Burdwan Division. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001176/2023-2024 | 05/RWS | 05/01/2024 | 12/01/2024 | KHUSI BHAKAT | 0.21 | 0 | 0 | 100
22 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 4 Nos Water Testing Laboratories under Burdwan Division, PHE Dte [Period:One Month (01.06.24 to 30.06.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/000111/2024-2025 | 298/AE/HQ | 30/05/2024 | 29/06/2024 | DULAL MAJUMDER | 0.87 | 0 | 0 | 100
23 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Supply of Residual Chlorine Kit, Iron Test Kit and Sample Collection Bottle for Burdwan District Laboratory under Burdwan Division, PHE Dte., Purba Bardhaman. | AE(HQs) | J.E. 1 BURDWAN | ORD/000697/2024-2025 | 863/AE/HQ | 24/10/2024 | 08/11/2024 | ALAKA GHOSH | 1 | 0 | 0 | 100
24 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 3 Nos Water Testing Laboratories under Burdwan Division, PHE Dte. [Period: For One Month (01.04.24 to 30.04.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/001217/2023-2024 | 235/AE/HQ | 28/03/2024 | 27/04/2024 | DULAL MAJUMDER | 0.87 | 0 | 0 | 100
25 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 3 Nos Water Testing Laboratories under Burdwan Division, PHE Dte. [Period: For One Month (01.05.24 to 31.05.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/000110/2024-2025 | 276/AE/HQ | 30/04/2024 | 31/05/2024 | DULAL MAJUMDER | 0.87 | 0 | 0 | 100
26 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary payment for the month of March'2024. |  |  | BILL/00191/2024-2025 | 295/JJM | 29/05/2024 | 29/05/2024 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
27 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Monthly Remuneration Of Lab Personnel For The Month Of September 2024 |  |  | BILL/00905/2024-2025 | 1044/JJM | 30/10/2024 | 30/10/2024 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
28 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | SALARY BILL FOR THE MONTH OF MAY-2024' |  |  | BILL/00262/2024-2025 | 459/JJM | 02/07/2024 | 02/07/2024 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
29 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary Bill For The Month Of September 2024 |  |  | BILL/00906/2024-2025 | 1043/JJM | 30/10/2024 | 30/10/2024 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
30 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Remuneration of Laboratory Personal for the month April-2024 |  |  | BILL/00261/2024-2025 | 370/JJM | 21/06/2024 | 21/06/2024 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
31 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Festival Bonus of lab personnel |  |  | BILL/00898/2024-2025 | 1032/JJM | 25/10/2024 | 25/10/2024 | AIKYATAN DEVELOPMENT SOCIETY | 0.18 | 0 | 0 | 0
32 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Laboratory contingency charges bill [Period January'22 to June'22] |  |  | BILL/00282/2024-2025 | 446/JJM | 02/07/2024 | 02/07/2024 | SIDHU KANU GRAM UNNAYAN SAMITY | 0.4 | 0 | 0 | 0
33 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Monthly remuneration of lab personnel for the month of July 2024 |  |  | BILL/00567/2024-2025 | 757/JJM | 30/08/2024 | 30/08/2024 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
34 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | SALARY BILL FOR THE MONTH OF MAY-2024. |  |  | BILL/00264/2024-2025 | 460/JJM | 02/07/2024 | 02/07/2024 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
35 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Grant The Remuneration Of Lab Staff For The Month Of November-2024 |  |  | BILL/01095/2024-2025 | 1175/JJM | 17/12/2024 | 17/12/2024 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
36 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | MAINTENANCE CHARGE FOR THE MONTH OF JANUARY 2024 TO JUNE 2024(6 MONTH) |  |  | BILL/00951/2024-2025 | 1049/JJM | 05/11/2024 | 05/11/2024 | SHASTRI SMRITI SANGHA | 0.4 | 0 | 0 | 0
37 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary Bill for the month of August- 2024 |  |  | BILL/00675/2024-2025 | 858/JJM | 20/09/2024 | 20/09/2024 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
38 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Grant The Remuneration Of Lab Staff For The Month Of October-2024. |  |  | BILL/01005/2024-2025 | 1086/JJM | 29/11/2024 | 29/11/2024 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
39 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary Bill for the month of April-2024 |  |  | BILL/00259/2024-2025 | 371/JJM | 21/06/2024 | 21/06/2024 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
40 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary bill for the month of July 2024 |  |  | BILL/00568/2024-2025 | 757/JJM | 30/08/2024 | 30/08/2024 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
41 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Grant The Festival Bonus For Laboratory personnel |  |  | BILL/00900/2024-2025 | 1034/JJM | 25/10/2024 | 25/10/2024 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.18 | 0 | 0 | 0
42 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary Bill For The Month Of November-2024 |  |  | BILL/01093/2024-2025 | 1174/JJM | 17/12/2024 | 17/12/2024 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
43 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Remuneration of lab personnel for the month of June 2024. |  |  | BILL/00556/2024-2025 | 747/JJM | 29/08/2024 | 29/08/2024 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
44 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | LABORATORY MAINTENANCE BILL FOR JANUARY TO JUNE 2024 |  |  | BILL/00952/2024-2025 | 1050/JJM | 05/11/2024 | 05/11/2024 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.4 | 0 | 0 | 0
45 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | SALARY BILL FOR THE MONTH OF MAY-2024' |  |  | BILL/00260/2024-2025 | 461/JJM | 02/07/2024 | 02/07/2024 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
46 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary bill for the month of June 2024 |  |  | BILL/00557/2024-2025 | 748/JJM | 29/08/2024 | 29/08/2024 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
47 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary payment for the month of March'2024. |  |  | BILL/00190/2024-2025 | 294/JJM | 29/05/2024 | 29/05/2024 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
48 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Remuneration of lab personnel for the month of August2024 |  |  | BILL/00676/2024-2025 | 857/JJM | 20/09/2024 | 20/09/2024 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
49 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Grant The Remuneration of Lab Staff for Month of June- 2024 |  |  | BILL/00558/2024-2025 | 749/JJM | 29/08/2024 | 29/08/2024 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
50 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Festival Bonus For The Lab Personnel |  |  | BILL/00899/2024-2025 | 1033/JJM | 25/10/2024 | 25/10/2024 | SHASTRI SMRITI SANGHA | 0.18 | 0 | 0 | 0
51 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Grant The Remuneration of Lab Staff For The Month Of September-2024 |  |  | BILL/00904/2024-2025 | 1045/JJM | 30/10/2024 | 30/10/2024 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
52 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Monthly remuneration for the month of October 2024 |  |  | BILL/01004/2024-2025 | 1087/JJM | 29/11/2024 | 29/11/2024 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
53 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary Bill for the month of October-2024 |  |  | BILL/01006/2024-2025 | 1088/JJM | 29/11/2024 | 29/11/2024 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
54 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Grant the Remuneration of lab staff for the month of April-2024. |  |  | BILL/00263/2024-2025 | 369/JJM | 21/06/2024 | 21/06/2024 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
55 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Monthly Remuneration Of Lab Personnel For The Month of November-2024 |  |  | BILL/01094/2024-2025 | 1176/JJM | 17/12/2024 | 17/12/2024 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
56 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Grant the remuneration of lab staff for the month of July 2024 |  |  | BILL/00566/2024-2025 | 757/JJM | 30/08/2024 | 30/08/2024 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
57 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary payment for the month of March'2024. |  |  | BILL/00189/2024-2025 | 293/JJM | 29/05/2024 | 29/05/2024 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
58 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Grant the remuneration of lab staff for the month of August-2024 |  |  | BILL/00677/2024-2025 | 856/JJM | 20/09/2024 | 20/09/2024 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
59 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work order for Supply & Delivery of Chemicals, reagents and consumables for 14(Fourteen) laboratories under Burdwan Division, P.H.E. Dte. [For s (six) Months] | AE(HQs) |  | ORD/000171/2025-2026 | 1825/BWD | 30/06/2025 | 30/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 19.69 | 0 | 0 | 0
60 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Annual Maintenance Contract (AMC) for software upgradation and other software related issues in existing computers, refilling of Cartridge of the printers, replacement of battery of UPS in District Lab (1No.), Sub-Dist. Lab (11Nos.) (Barshul SDWTL, Satgachia SDWTL, Monteswar SDWTL, Sankari SDWTL, Anukhal SDWTL, Saktigarh SDWTL, Parulia SDWTL, Ganganandapur SDWTL, Sehera SDWTL, Bonnobogram SDWTL, Ketugram SDWTL) and NGO Lab (2Nos.) (Shastri Smriti Sangha&Aikyatan Development Society) under Burdwan Division, P.H.E. Dte. [Period from 01.02.2025 to 31.07.2025 i.e. Six Months] |  | J.E. 1 BURDWAN | ORD/001271/2024-2025 | 166/AE/HQ | 31/01/2025 | 31/07/2025 | COMPUTER MEDIA | 0.99 | 0 | 0 | 0
61 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Supply of Residual Chlorine Kit and engagement of Laboratory personnel (Chemist/Bacteriologist/ Lab Assistant and Sampling Assistant) including maintenance in 4 Nos. Sub District Laboratories within Kalna Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period For Six Months] i.e. period from 01.08.2025 to 31.01.2026. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000427/2025-2026 | 2227/BWD | 01/08/2025 | 01/02/2026 | DULAL MAJUMDER | 20.51 | 0 | 0 | 0
62 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Supply of Residual Chlorine Kit and engagement of Laboratory personnel (Chemist/Bacteriologist/ Lab Assistant and Sampling Assistant) including maintenance in 1 No. Sub District Laboratory within Durgapur Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01.08.2025 to 31.08.2025 i.e. 1 (one) Month] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000342/2025-2026 | 2206/BWD | 01/08/2025 | 01/09/2025 | DULAL MAJUMDER | 0.8 | 0 | 0 | 0
63 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Arrear salary (From January'23 to August'23) for the laboratory personnel (Bacteriologist, Laboratory Assistant) of Bonnabagram Subdivision laboratory under Durgapur Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000688/2023-2024 | 899/DSD | 13/12/2023 | 28/12/2023 | CLIFFORD FACILITY SERVICES PVT.LTD. | 0.66 | 0 | 0 | 100
64 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | SupervisionandextendsupporttoNABLrecognizedWaterQualityTestingBlocklevelLaboratoryunderTheExecutiveEngineer,BurdwanDivision,PublicHealthEngineeringDirectorate,GovernmentofWestBengalbyassigningteamofcompetentresourcepersonnelwhowillbeengagedforcompletesupervisionforretainingNABLrecognitionandcompilationofpreparatoryup-to-datedocumentation,Calibrationforon-sitesurveillancebyNABL(asperNABL139)foraperiodofonemonthfromthedateofcommencement.(NameofSDL: Sankari Sub District Water Testing Laboratory under Burdwan Sadar Sub Division.) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000976/2023-2024 | 3059/BSD | 29/12/2023 | 12/02/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
65 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | SupervisionandextendsupporttoNABLrecognizedWaterQualityTestingBlocklevelLaboratoryunderTheExecutiveEngineer,BurdwanDivision,PublicHealthEngineeringDirectorate,GovernmentofWestBengalbyassigningteamofcompetentresourcepersonnelwhowillbeengagedforcompletesupervisionforretainingNABLrecognitionandcompilationofpreparatoryup-to-datedocumentation,Calibrationforon-sitesurveillancebyNABL(asperNABL139)foraperiodofonemonthfromthedateofcommencement.(NameofSDL:Sehera Sub District Water Testing Laboratory under Burdwan Sadar Sub Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000977/2023-2024 | 3060/BSD | 29/12/2023 | 12/02/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.51 | 0 | 0 | 100
66 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work order for Engagement of Laboratory personnel (Chemist/Bacteriologist/ Lab Assistant in 1 No. Ketugram Sub District Water Testing Laboratory within Katwa sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period For 01.01.2025 to 31.01.2025] [Sl No -01] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001194/2024-2025 | 1812/KTS | 31/12/2024 | 31/01/2025 | JAGADHATRI CONSTRUCTION AND BUILDERS | 0.59 | 0 | 0 | 100
67 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 3 Nos Water Testing Laboratories under Burdwan Division, PHE Dte. [Period: For One Month (01.07.24 to 31.07.24)] | AE(HQs) | J.E. 1 BURDWAN | ORD/000476/2024-2025 | 374/AE/HQ | 01/07/2024 | 01/08/2024 | DULAL MAJUMDER | 0.87 | 0 | 0 | 100
68 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Engagement of Laboratory personnel (Chemist/Bacteriologist/ Lab Assistant in 1 No. Ketugram Sub District Water Testing Laboratory within Katwa sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period For 01 Months] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001054/2024-2025 | 1660/KTS | 26/11/2024 | 26/12/2024 | JAGADHATRI CONSTRUCTION AND BUILDERS | 0.59 | 0 | 0 | 100
69 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Sampling Assistant) in Bananabagram Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period for 01.06.2024 to 31.07.2024]. | AE(HQs) | J.E. 1 BURDWAN | ORD/000430/2024-2025 | 303/AE/HQ | 31/05/2024 | 31/07/2024 | DULAL MAJUMDER | 0.25 | 0 | 0 | 100
70 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Salary bill (from January 2024 to February 2024) for the laboratory personnel (Bacteriologist, Laboratory Assistant) of Bonnabagrum Sub-Division laboratory under Durgapur Sub-Division, P.H.E. DTE. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001274/2023-2024 | 994/DSD | 29/12/2023 | 03/03/2024 | CLIFFORD FACILITY SERVICES PVT.LTD. | 0.63 | 0 | 0 | 100
71 | PURBA BARDHAMAN |  | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19071 | Support-WQMSP | Supply & Delivery of Chemicals, reagents and consumables for 14(Fourteen) laboratories under Burdwan Division, P.H.E. Dte. | AE(HQs) | J.E. 1 BURDWAN | ORD/000710/2024-2025 | 3712/BWD | 28/10/2024 | 27/11/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 39.74 | 0 | 0 | 100
Total | [13 empty] | 156.19 | 0 | 0