## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19072 | Support-WQMSP | Carriage of FTK Box to different BMOH office under Burdwan Division, PHE. Dte. | AE(HQs) | J.E. 1 BURDWAN | ORD/000140/2024-2025 | 308/AE/HQ | 10/06/2024 | 20/06/2024 | KHUSI BHAKAT | 0.29 | 0.29 | 100 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19072 | Support-WQMSP | Hire Charges of Training Car & Carriage of FTK Box to different BMOH offices under Burdwan Division, PHE. Dte. | AE(HQs), Burdwan Division, PHE Dte. | Junior Engineer, Burdwan Division | ORD/000634/2025-2026 | 1130/AE/HQ | 11/09/2025 | 26/09/2025 | KHUSI BHAKAT | 0.52 | 0 | 0 | 0
Total | [13 empty] | 0.81 | 0.29 | 35.45