## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19072 | Support-WQMSP | Carriage of FTK Box to different BMOH office under Burdwan Division, PHE. Dte. | AE(HQs) | J.E. 1 BURDWAN | ORD/000140/2024-2025 | 308/AE/HQ | 10/06/2024 | 20/06/2024 | KHUSI BHAKAT | 0.29 | 0.29 | 100 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19072 | Support-WQMSP | Uploading charges of all collected & tested data management to State WQ Dashboard using FTK/H2S vials for FHTCs in Burdwan district related to Water Quality Monitoring & Surveillance Activities under Jal Jeevan Mission. | AE(HQs) | J.E. 1 BURDWAN | ORD/001296/2024-2025 | 353/AE/HQ | 10/03/2025 | 09/04/2025 | ALAKA GHOSH | 4.65 | 0 | 0 | 100
Total | [13 empty] | 4.93 | 0.29 | 5.79