## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RAINA (PART-B) PWSS TO ACCOMODATE FHTC IN RAINA-I BLOCK WITH IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE. | SM/19113 | Augmentation | Construction of boundary wall (128.40 Mtr.) including switch room at 3rd tube well site (New) of Aug. of RAINA and its adj. mouzas Piped W/S. Scheme under Budwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000185/2024-2025 | 2398/BWD | 26/06/2024 | 01/07/2025 | RANADHIR SINHA | 19.41 | 0 | 0 | 82
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RAINA (PART-B) PWSS TO ACCOMODATE FHTC IN RAINA-I BLOCK WITH IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE. | SM/19113 | Augmentation | Balance work OHR Connection, Platform, Laying Parallel Pipeline, providing FHTC, Construction of Boundary Wall, Drain & Pathway at Head Work site & Repairing of Pump House at Head Work site & 2nd Tube Well Site for AUGMENTATION OF RAINA PIPED WATER SUPPLY SCHEME, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000173/2024-2025 | 2268/BWD | 18/06/2024 | 01/07/2025 | RANADHIR SINHA | 96.75 | 0 | 0 | 65
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RAINA (PART-B) PWSS TO ACCOMODATE FHTC IN RAINA-I BLOCK WITH IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE. | SM/19113 | Augmentation | Repairing and restore pipe line dammaged by laying of pipeline at different location of Augmentation of RAINA and its adjoining mouza's Piped W/S Scheme at Raina-I Block within Burdwan Sub Division under Burdwan Division, P.H.E. Dte |  |  | ORD/001001/2023-2024 | 118/BSD | 18/01/2024 | 17/02/2024 | POMPA CONSTRUCTION CO. | 0.94 | 0.94 | 99.89 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RAINA (PART-B) PWSS TO ACCOMODATE FHTC IN RAINA-I BLOCK WITH IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE. | SM/19113 | Augmentation | Restoration of village road damaged by laying pipeline at Nandipara Kalitala,Ranapara and Raina Co-Operative Society of Augmentation of Raina Water Supply Scheme at Raina-I Block within under Burdwan Division,PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000999/2023-2024 | 117/BSD | 18/01/2024 | 02/02/2024 | SOUMYAVASH DAS | 0.92 | 0.91 | 99 | 100
Total | [13 empty] | 118.02 | 1.85 | 1.57