## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Solarisation of WBSEDCL energised electrical installations of PWSS of different Blocks in the district Purba Bardhaman under Central Mechanical Division, PHE Dte. | ASSISTANT ENGINEER,Driller In-Charge | Junior Engineer | ORD/000131/2023-2024 | 2693/CMD | 23/06/2023 | 23/12/2023 | A K INDUSTRIES | 203.81 | 197.82 | 97.06 | 95
2 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Quotation for load enhancement of Mugura PWSS (Solar) |  |  | BILL/00231/2024-2025 | BP-2024-25-123 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.2 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Electric quotation for installation of Solar Power plant at Sasinara W/S Zone-I |  |  | BILL/00313/2024-2025 | BP-2024-25-153 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Quotation for Solar power plant at NATU PWSS (Solar). |  |  | BILL/00394/2024-2025 | BP-2024-25-210 | 18/07/2024 | 18/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Quotation for load enhancement of Natu PWSS (Solar) |  |  | BILL/00233/2024-2025 | BP-2024-25-124 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.21 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | New solar connection for Patuli PWSS . |  |  | BILL/02402/2023-2024 | BP-2023-24-575 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.32 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Quotation for load enhancement of Tendual PWSS (Solar) |  |  | BILL/00232/2024-2025 | BP-2024-25-125 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.33 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Quotation for Solar power plant at Tendul PWSS (Solar). |  |  | BILL/00393/2024-2025 | BP-2024-25-209 | 18/07/2024 | 18/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Application for Solar power plant at Sasinara Zone-I, TW 1 |  |  | BILL/00444/2024-2025 | BP-2024-25-233 | 30/07/2024 | 30/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Application fees for connectivity of solar plant metering system at Kaithan W/W No.-1 Sadarghat |  |  | BILL/00375/2024-2025 | BP-2024-25-185 | 08/07/2024 | 08/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | New solar connection for Parulia PWSS . |  |  | BILL/02403/2023-2024 | BP-2023-24-576 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.31 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Quotation for for application fee for new smart export import meter for a new solar plant at Khandaghosh PH-I PWSS (Solar) |  |  | BILL/00234/2024-2025 | BP-2024-25-122 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Quotation for solar power plant at Mugura PWSS. |  |  | BILL/00387/2024-2025 | BP-2024-25-211 | 18/07/2024 | 18/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Application fees solar power plant at jageswardihi |  |  | BILL/01470/2025-2026 |  | 10/09/2025 | 10/09/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Wbsedcl Quotation for Solar Application fee at Kashipur Pwss Ph-01 |  |  | BILL/02103/2025-2026 |  | 21/11/2025 | 21/11/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
16 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | WBSEDCL SOLAR QUOTATION |  |  | BILL/01880/2024-2025 | 74 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.22 | 0 | 0 | 0
17 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Wbsedcl Quotation for installation of import /export meter (Solar) at Jougram Pwss Ph-01 |  |  | BILL/00316/2025-2026 | 74 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.22 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | WBSEDCL Application fees for the installation of import/export energy meter (solar) at Deriapur Pwss, P/H-I |  |  | BILL/01243/2025-2026 | 74 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.18 | 0 | 0 | 0
19 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | WBSEDCL Quotation for the installation of import/export energy meter (solar) at Ramkrishnapur Pwss. |  |  | BILL/01264/2025-2026 |  | 29/08/2025 | 29/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.15 | 0 | 0 | 0
20 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | WBSEDCL Application fees for the installation of import/export energy meter (solar) at Rasuikhanda Pwss, P/H-I503427341 |  |  | BILL/01424/2025-2026 |  | 09/09/2025 | 09/09/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
21 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Wbsedcl Quotation for Solar Application at Digra Pwss Ph-01 |  |  | BILL/02340/2025-2026 |  | 10/12/2025 | 10/12/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
22 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Wbsedcl Quotation for Solar Application at Chak Bataspur Pwss Ph-01 |  |  | BILL/02341/2025-2026 |  | 10/12/2025 | 10/12/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
23 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Wbsedcl Quotation for Solar Application at Chotobainan Pwss Ph-01 |  |  | BILL/02338/2025-2026 |  | 10/12/2025 | 10/12/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
24 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Quotation for Solarization of Baharan PWSS(HW site) |  |  | BILL/01828/2024-2025 | 74 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
25 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Wbsedcl Quotation for installation of import /export meter (Solar) at Sasinara zone-1 Pwss Ph-01 |  |  | BILL/00063/2025-2026 | 73 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.22 | 0 | 0 | 0
26 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | WBSEDCL Application fees for the installation of import/export energy meter (solar) at Palashan Pwss, P/H-I |  |  | BILL/02306/2025-2026 |  | 03/12/2025 | 03/12/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
27 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | QUOTATION FOR APPLICATION FEES FOR SOLAR POWER PLANT AT GALSI PWSS UNDER CMD, PHE, Dte. |  |  | BILL/01196/2025-2026 |  | 25/08/2025 | 25/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
28 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Wbsedcl Quotation for Solar Application at Kamarhati Pwss Ph-01 |  |  | BILL/02339/2025-2026 |  | 10/12/2025 | 10/12/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
29 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Wbsedcl Quotation for Application fee receipt (Solar) at Bamangaria Pwss Ph-01 |  |  | BILL/01660/2025-2026 |  | 25/09/2025 | 25/09/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
30 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | WBSEDCL Application fees for the installation of import/export energy meter (solar) at Ramkrishnapur Pwss, P/H-I |  |  | BILL/01826/2024-2025 | 74 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
31 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | WBSEDCL Application fees for the installation of import/export energy meter (solar) at Anguna Pwss, P/H-I |  |  | BILL/00312/2025-2026 | 74 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.22 | 0 | 0 | 0
32 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Quotation for Solarization of the Ketugram PWSS (HW site) |  |  | BILL/01835/2024-2025 | 74 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
33 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Wbsedcl Quotation for installation of import /export meter (Solar) at Rasulpur Pwss Ph-01 |  |  | BILL/00062/2025-2026 | 73 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.15 | 0 | 0 | 0
34 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Application fee for solar power |  |  | BILL/00290/2025-2026 | 73 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
35 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Wbsedcl Quotation for installation of import /export meter (Solar) at Rasulpur Pwss Ph-01 |  |  | BILL/00413/2025-2026 | 74 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.15 | 0 | 0 | 0
36 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | WBSEDCL SOLAR QUOTATION |  |  | BILL/01879/2024-2025 | 74 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.22 | 0 | 0 | 0
37 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | QUOTATION FOR INSTALLATION OF SOLAR METER AT CHAKTENTUL PWSS UNDER CMD, PHE, Dte. |  |  | BILL/01075/2025-2026 |  | 14/08/2025 | 14/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.22 | 0 | 0 | 0
38 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Wbsedcl Quotation for installation of import /export meter (Solar) at Nabagram Pwss Ph-01 |  |  | BILL/00313/2025-2026 | 74 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.29 | 0 | 0 | 0
39 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | APPLICATION FEE FOR SOLARIZATION OF CHAKTENTUL H/W SITE |  |  | BILL/00253/2025-2026 | 73 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
40 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | SOLAR QUOTATION FOR SARANGA PH-1 |  |  | BILL/01263/2025-2026 |  | 29/08/2025 | 29/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
41 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | SOLAR QUOTATION DOR SANKARI PH-1 |  |  | BILL/01323/2025-2026 |  | 02/09/2025 | 02/09/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
42 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | WBSEDCL Application fees for the installation of import/export energy meter (solar) at Manikhar Pwss, P/H-I |  |  | BILL/01324/2025-2026 |  | 02/09/2025 | 02/09/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
43 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Wbsedcl Quotation for installation of import /export meter (Solar) at Madhabpur zone-1 Pwss Ph-01 |  |  | BILL/00314/2025-2026 | 74 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.21 | 0 | 0 | 0
44 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Wbsedcl Quotation for installation of import /export meter (Solar) at Nabagram Pwss Ph-01 |  |  | BILL/00064/2025-2026 | 73 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.43 | 0 | 0 | 0
45 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | WBSEDCL Application fees for the installation of import/export energy meter (solar) at Deriapur Pwss, P/H-I |  |  | BILL/00315/2025-2026 |  | 11/06/2025 | 11/06/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.04 | 0 | 0 | 0
46 | PURBA BARDHAMAN |  | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman | SM/17188 | Solarisation | Application fee for solar plant at ura head works site. |  |  | BILL/00510/2026-2027 |  | 26/05/2026 | 26/05/2026 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
Total | [13 empty] | 208.26 | 197.82 | 94.99