## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | Providing service by assigning technical resource team for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Krishnaganj Sub-District Water Testing Laboratory under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000101/2021-2022 | 215/KLYSD1 | 22/07/2021 | 22/10/2021 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 4.83 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | SUPPLY OF CHEMICAL , GLASSWARE, AND INSTRUMENT .... NADIA LABORATORY, KALYANI, NADIA |  |  | VCH/000759/2020-2021 | 338/DW | 11/01/2021 | 11/01/2021 | LAXMI ENTERPRISE | 26.1 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | URGENT SUPPLY SILVER - DIETHYL-DITHIO-CARBONATE AND MTC OF WATER QUALITY ..................TESTING LAB |  |  | VCH/000368/2021-2022 | 148/LAB | 10/09/2021 | 10/09/2021 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.97 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | SUPPLY OF CHEMICALS AND COSUMABLE FOR OP & MTC OF WATER QUALITY ANALYSIS AT DIFFERENT WATER TESTING LABORATORIES IN NADIA DISTRICT UNDER NADIA DIVISION , PHE , DTE. |  |  | VCH/000680/2021-2022 | 311/DW | 02/11/2021 | 02/11/2021 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 4.98 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | PROVIDING SERVICE BY TECHNICAL RESOURCE ....... KRISHNAGAR SUB. DIST. LABORATORY |  |  | VCH/000683/2021-2022 | 311/DW | 02/11/2021 | 02/11/2021 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 3.66 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | PROVIDING SERVICE BY TECHNICAL RESOURCE ....... HABIBPUR SUB. DIST. LABORATORY |  |  | VCH/000681/2021-2022 | 311/DW | 02/11/2021 | 02/11/2021 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 3.66 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | PROVIDING SERVICE BY TECHNICAL RESOURCE ....... TEHATTA SUB. DIST. LABORATORY |  |  | VCH/000684/2021-2022 | 311/DW | 02/11/2021 | 02/11/2021 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 3.66 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | URGENT SUPPLY SILVER - DIETHYL-DITHIO-CARBONATE AND MTC OF WATER QUALITY ..................TESTING LAB |  |  | VCH/000367/2021-2022 | 148/LAB | 10/09/2021 | 10/09/2021 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.96 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | PROCUREMENT OF CONSUMABLE FOR OMAS ( ON SITE MOBILE ANALYSIS SYSTEM ) AS DIRECTED LAY EIC UNDER NADIA DIVISION, PHE, DTE. |  |  | VCH/000304/2021-2022 | 141/LAB | 17/08/2021 | 17/08/2021 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 4.29 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | ANNUAL SERVISES CONTRACT FOR DOUBLE BEAM .......AT BELPUKUR WTP SITE , NADIA |  |  | VCH/000450/2021-2022 | 203/DW | 22/09/2021 | 22/09/2021 | TARUN KUMAR BHATTACHARYA | 3.85 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | SUPPLY , INSTALLATION , AND COMMISSIONING OF 15KVA UPS BATTERY ETC IN THE DISTRICT LABORATORY |  |  | VCH/000996/2020-2021 | 414/UPS | 08/03/2021 | 08/03/2021 | OTHERS | 8.45 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | COMPUTER PURCHASED THROUGH GEMS |  |  | VCH/000372/2021-2022 | 167/GEM | 09/09/2021 | 09/09/2021 | IONET | 3.82 | 0 | 0 | 0
13 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | ANNUAL SERVICE CONTRACT FOR DOUBLE BEAM ATOMIC ABSOPTION SPECTROMETER AA53300........SPARS PARTS . |  |  | VCH/000369/2021-2022 | 148/LAB | 10/09/2021 | 10/09/2021 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 4.56 | 0 | 0 | 0
14 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | MTC FOR COMPUTERS .... NADIA DIST. LAB. |  |  | VCH/000371/2021-2022 | 168/LAB | 13/09/2021 | 13/09/2021 | IONET | 0.92 | 0 | 0 | 0
15 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | INRACSTRUCTURE DEVELOPMENT REGARDING NABL .... NADIA DIVISION, PHE, DTE |  |  | VCH/000452/2021-2022 | 203/DW | 22/09/2021 | 22/09/2021 | SUMAN CHAKRABORTY | 1.98 | 0 | 0 | 0
16 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | CONSTRUCTION OF SAMPLE COLLECTION .... TESTING LABORATORY |  |  | VCH/000448/2021-2022 | 203/DW | 22/09/2021 | 22/09/2021 | B.P. ENTERPRISE | 1 | 0 | 0 | 0
17 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | WATER SAMPLE COLLECTION FROM STREET STAND POST ... NADIA DISTRICT |  |  | VCH/000366/2021-2022 | 148/LAB | 10/09/2021 | 10/09/2021 | LOKNATH ENTERPRISE | 4.25 | 0 | 0 | 0
18 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | PROVIDING SERVICE BY TECHNICAL RESOURCE .......BAGULA SUB. DIST. LABORATORY |  |  | VCH/000682/2021-2022 | 311/DW | 02/11/2021 | 02/11/2021 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 3.66 | 0 | 0 | 0
19 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | PROVIDING CONSULTANCY SERVISES INCLUDING SUPPLY WATER TESTING LABORATORY |  |  | VCH/000449/2021-2022 | 203/DW | 22/09/2021 | 22/09/2021 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 2.31 | 0 | 0 | 0
20 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | Supply and installation of Sign-Board for NABL Accredited/Recognized drinking Water Testing Laboratories under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000208/2022-2023 | 1021/Kly SD-1 | 10/11/2022 | 25/11/2022 | MANISHIKA CONSTRUCTION | 0.45 | 0.45 | 100 | 0
21 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | SUPPLY OF LABORATORY CHEMICAL .........NADIA DIVISION, PHE, DTE |  |  | VCH/000764/2021-2022 | 400/DW | 17/12/2021 | 17/12/2021 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 3.38 | 0 | 0 | 0
22 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | Annual Service contract for Double beam Atomic Absorption Spectrometer AAS3300 including supply of necessary spare parts and consumables (As and when required) installed at Nadia District Water Testing Laboratory At Haringhata WTP Site, Nadia, under Nadia Division, PHE Dte.(W.E.F-01.08.2021 to 31.07.2022) | Assistant Engineer |  | ORD/000121/2021-2022 | 229/Kly SD-1 | 27/07/2021 | 27/07/2022 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 4.06 | 0 | 0 | 0
23 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | Supply of Containers for chemical and bacteriological testing at Different Water Testing Laboratories under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000304/2022-2023 | 1161/Kly SD-I | 16/12/2022 | 31/12/2022 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.99 | 0.99 | 100 | 0
24 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | Supply of Chemicals & Consumables at Different Water Testing Laboratories and Calibration of Instruments & Glassware at Nadia District Water Testing Laboratory under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000207/2022-2023 | 1020/Kly SD-1 | 10/11/2022 | 25/11/2022 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.99 | 0.99 | 100 | 0
25 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | Supply and installation of Fire Extinguisher at Nadia District Water Testing Laboratory and PHE Complex, Bhander under Nadia Division, PHE Dte | Assistant Engineer |  | ORD/000416/2022-2023 | 184/Kly SD-I | 13/02/2023 | 28/02/2023 | MRINAL DASGUPTA | 0.94 | 0.94 | 100 | 0
26 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | SUPPLY OF SCANDISK PEN DRIVE WITH 256 GB STORAGE CAPACITY AND 1 YEAR WARRANTY. SCUDA SSD SATA 256 GB (SSCS 256 GB SATA SSD) WITH CASING 9 NOS. |  |  | BILL/00495/2022-2023 | 428/PFMS | 22/02/2023 | 22/02/2023 | EASY DAY ENTERPRISE | 0.24 | 0 | 0 | 0
27 | NADIA |  | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. | SM/06631 | Support-WQMSP | Supply of Microtek Line Interactive UPS LEGEND 650VA UPS of Office of the Executive Engineer, Nadia Division, P.H. Engineering Dte. |  |  | BILL/00323/2022-2023 | 414/PFMS | 08/02/2023 | 08/02/2023 | IONET | 0.34 | 0 | 0 | 0
Total | [13 empty] | 99.29 | 3.38 | 3.4