## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing consultancy services including supply of necessary instruments, chemicals and glass ware for NABL Accreditation of Nadia District Water Testing Laboratory, Kalyani. | SM/06873 | Support-WQMSP | SUPPLY OF RESIDUAL CHLORINE TESTING UNIT KIT .........NADIA , DIVISION, PHE, DTE |  |  | VCH/000781/2020-2021 | 377/DW | 27/01/2021 | 27/01/2021 | MRINAL DASGUPTA | 0.81 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing consultancy services including supply of necessary instruments, chemicals and glass ware for NABL Accreditation of Nadia District Water Testing Laboratory, Kalyani. | SM/06873 | Support-WQMSP | PROVIDING CONSULTANCY SERVICE INCLUDING SUPPLY OF NECESSARY INSTRUMENT ......WATER TESTING LAB AT KALYANI |  |  | VCH/001029/2020-2021 | 458/DW | 30/03/2021 | 30/03/2021 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 16.28 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing consultancy services including supply of necessary instruments, chemicals and glass ware for NABL Accreditation of Nadia District Water Testing Laboratory, Kalyani. | SM/06873 | Support-WQMSP | SUPPLY, DELIVERY, INSTALLATION, ........NADIA, DIVSION, PHE, DTE. |  |  | VCH/000782/2020-2021 | 377/DW | 27/01/2021 | 27/01/2021 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.99 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing consultancy services including supply of necessary instruments, chemicals and glass ware for NABL Accreditation of Nadia District Water Testing Laboratory, Kalyani. | SM/06873 | Support-WQMSP | RECURRING EXPENDITURE OF LABORATORIES (NABL) |  |  | VCH/000181/2021-2022 | 62/NABL | 08/07/2021 | 08/07/2021 | OTHERS | 0.06 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing consultancy services including supply of necessary instruments, chemicals and glass ware for NABL Accreditation of Nadia District Water Testing Laboratory, Kalyani. | SM/06873 | Support-WQMSP | INRACSTRUCTURE DEVELOPMENT REGARDING NABL .... NADIA DIVISION, PHE, DTE |  |  | VCH/000452/2021-2022 | 203/DW | 22/09/2021 | 22/09/2021 | SUMAN CHAKRABORTY | 1.98 | 0 | 0 | 0
Total | [13 empty] | 20.12 | 0 | 0