## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Fatepur Water Supply Scheme under Jal Swapno Program in Nadia District | SM/06995 | Retrofitting | EXTENSION OF PIPE LINE FOR FHTC KALIGANJ, PART-1 Z-IV |  |  | VCH/000374/2021-2022 | 174/FHTC | 10/09/2021 | 10/09/2021 | UMWELT ENGINEERS PVT LTD | 4.71 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Fatepur Water Supply Scheme under Jal Swapno Program in Nadia District | SM/06995 | Retrofitting | EXTENSION OF PIPE LINE FOR FHTC KALIGANJ, PART-1 Z-IV |  |  | VCH/000375/2021-2022 | 174/FHTC | 10/09/2021 | 10/09/2021 | UMWELT ENGINEERS PVT LTD | 4.58 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Fatepur Water Supply Scheme under Jal Swapno Program in Nadia District | SM/06995 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PIPE G.I/PVC PIPE OF AVERAGE LENGTH OF 10MM DIA GUN-METAL FERRULE, SADDLE PIECE 15MM DIA BIB COCK ETC AT SUBERNA BIHAR W/S SCHEME PART-B |  |  | VCH/000963/2021-2022 | 473/DW | 07/02/2022 | 07/02/2022 | ROY CONSTRUCTION | 0.73 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Fatepur Water Supply Scheme under Jal Swapno Program in Nadia District | SM/06995 | Retrofitting | Providing functional household tap connection(Part) including supply of 15mm dia PVC pipe of average length of 15mm,10mm dia Gun-Metal Ferrule,Saddle piece(as required size) 15mm dia cock etc. all complete from Fatepur W/S Scheme in Nadia District under Nadia Division P.H.E.Dte. | Assistant Engineer |  | ORD/000219/2020-2021 | 4081/ND | 31/12/2020 | 31/03/2021 | MONDAL PRECISION PRIVATE LIMITED | 96.54 | 80.47 | 83.35 | 0
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Fatepur Water Supply Scheme under Jal Swapno Program in Nadia District | SM/06995 | Retrofitting | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Executive Engineer, Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000749/2021-2022 | 286/Kly SD-I | 31/03/2022 | 31/03/2023 | ARROWTOWN DEALERS PVT. LTD | 4.8 | 0 | 0 | 0
Total | [13 empty] | 111.36 | 80.47 | 72.26