## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-A). | SM/06996 | Retrofitting | PREPERATION OF DETAILS PROJECT FOR FHTC AT SURFACE WATER BASED W/S SCHEME ( N.SECTOR) , PART-II, ZONE-I, PHASE-A & B UNDER , NADIA DIVISION , PHE ,DTE |  |  | VCH/000307/2021-2022 | 139/FHTC | 17/08/2021 | 17/08/2021 | LEMNISCATE | 0.45 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-A). | SM/06996 | Retrofitting | PREPERATION OF DETAILS PROJECT FOR FHTC AT SURFACE WATER BASED W/S SCHEME ( N.SECTOR) , PART-II, ZONE-I, PHASE-A & B UNDER , NADIA DIVISION , PHE ,DTE |  |  | VCH/000311/2021-2022 | 139/FHTC | 17/08/2021 | 17/08/2021 | LEMNISCATE | 0.48 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-A). | SM/06996 | Retrofitting | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H.E. Dte., Kalyani, Nadia. Period of work 01-03-2022 to 28-02-2023 | Assistant Engineer |  | ORD/000814/2021-2022 | 118/RSD | 28/02/2022 | 05/11/2022 | SUMAN CHAKRABORTY | 3.85 | 0.97 | 25.28 | 75
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-A). | SM/06996 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(Northern Sector), Part-I,Zone-I within Kaliganj Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000221/2020-2021 | 4083/ND | 31/12/2020 | 31/03/2021 | ALOKE ENTERPRISE | 97.02 | 89.26 | 92.01 | 100
5 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-A). | SM/06996 | Retrofitting | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-03-2021 to 28-02-2022 (250 working days) | Assistant Engineer |  | ORD/000501/2020-2021 | 172/RSD | 22/02/2021 | 22/02/2022 | SUMAN CHAKRABORTY | 3.85 | 0.75 | 19.38 | 0
Total | [13 empty] | 105.64 | 90.98 | 86.12