## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-B). | SM/06997 | Retrofitting | Additional work for extension of pipe line at Hutguchha, basorkhola & Kaliganj for Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Kaliganj Block (Phase-c). |  |  | VCH/000955/2021-2022 | 562/DW | 25/02/2022 | 25/02/2022 | M/S NIBHAS SINHA | 4.65 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-B). | SM/06997 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(Northern Sector),Part-I,Zone-I Within Kaliganj Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000216/2020-2021 | 4080/ND | 31/12/2020 | 31/03/2021 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 97.03 | 86.99 | 89.66 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-B). | SM/06997 | Retrofitting | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Executive Engineer, Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000749/2021-2022 | 286/Kly SD-I | 31/03/2022 | 31/03/2023 | ARROWTOWN DEALERS PVT. LTD | 4.8 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-B). | SM/06997 | Retrofitting | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-03-2021 to 28-02-2022 (250 working days) | Assistant Engineer |  | ORD/000501/2020-2021 | 172/RSD | 22/02/2021 | 22/02/2022 | SUMAN CHAKRABORTY | 3.85 | 0 | 0 | 0
Total | [13 empty] | 110.32 | 86.99 | 78.85