## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-IV within Kaliganj Block (Phase-A). | SM/06998 | Retrofitting | PREPERATION OF DETAILS PROJECT FOR FHTC AT SURFACE WATER BASED W/S SCHEME ( N.SECTOR) , PART-II, ZONE-I, PHASE-A & B UNDER , NADIA DIVISION , PHE ,DTE |  |  | VCH/000308/2021-2022 | 139/FHTC | 17/08/2021 | 17/08/2021 | LEMNISCATE | 0.44 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-IV within Kaliganj Block (Phase-A). | SM/06998 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(Northern Sector),Part-I,Zone-IV within Kaliganj Block(Phase-A) in Nadia District under Nadia Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000220/2020-2021 | 4082/ND | 31/12/2020 | 31/03/2021 | UMWELT ENGINEERS PVT LTD | 96.95 | 92.52 | 95.43 | 0
Total | [13 empty] | 97.39 | 92.52 | 95