## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-A). | SM/06999 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT NORTHERN SECTORPART-1 Z-3 |  |  | VCH/001079/2020-2021 | 447/DW | 25/03/2021 | 25/03/2021 | M/S S & P CONSTRUCTION | 18.28 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-A). | SM/06999 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-III within Kaliganj block(Phase-A) in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000184/2020-2021 | 3590/ND | 08/12/2020 | 08/03/2021 | M/S S & P CONSTRUCTION | 97.06 | 144.5 | 148.88 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-A). | SM/06999 | Retrofitting | Continuation of Hiring Diesel cab having contract permit from regional transport authority for the office use of the Assistant Engineer, Kalyani Sub-Division-1, Nadia Division PHE Dte at D.C Building, Kalyani, Nadia w.e.f 01/10/2021 to 31/03/2022 (6 months)) | Assistant Engineer |  | ORD/000272/2021-2022 | 441/Kly SD-I | 30/09/2021 | 31/03/2022 | SATYABRATA CHAKRABORTY | 2.4 | 0.54 | 22.35 | 0
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-A). | SM/06999 | Retrofitting | Hiring Diesel Maxi Cub having car No WB-51/B-3194 for office of the Assistant Engineer, RWS Nadia Sub-Division, PHE Dte. for the period from 01.08.2021 to 31.07.2022 | Assistant Engineer |  | ORD/000951/2021-2022 | 896/PH | 30/07/2021 | 30/07/2022 | TARUN KUMAR BHATTACHARYA | 4.8 | 0.51 | 10.67 | 100
Total | [13 empty] | 122.54 | 145.55 | 118.78