## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-IV within Kaliganj Block (Phase-B). | SM/07001 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT NORTHERN SECTORPART-1 Z-4 |  |  | VCH/001078/2020-2021 | 446/DW | 25/03/2021 | 25/03/2021 | M/S NIBHAS SINHA | 28.95 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-IV within Kaliganj Block (Phase-B). | SM/07001 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-IV within Kaliganj block(Phase-B) in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000187/2020-2021 | 3593/ND | 08/12/2020 | 08/03/2021 | M/S NIBHAS SINHA | 96.81 | 131.5 | 135.83 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-IV within Kaliganj Block (Phase-B). | SM/07001 | Retrofitting | Hiring of Diesel Ambassador Car/maxi cab for the office of the Assistant Engineer, Debagram Sub-Division, P.H. Engineering Dte., Debagram, Nadia with effect from 01/08/22 to 31/07/23 | Assistant Engineer |  | ORD/000186/2022-2023 | 312/D/DSD | 29/07/2022 | 29/07/2023 | TARUN KUMAR BHATTACHARYA | 4.8 | 1.54 | 32.03 | 70
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-IV within Kaliganj Block (Phase-B). | SM/07001 | Retrofitting | Hiring Diesel Maxi Cub having car No WB-51/B-3194 for office of the Assistant Engineer, RWS Nadia Sub-Division, PHE Dte. for the period from 01.08.2021 to 31.07.2022 | Assistant Engineer |  | ORD/000951/2021-2022 | 896/PH | 30/07/2021 | 30/07/2022 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0 | 100
Total | [13 empty] | 135.36 | 133.03 | 98.28