## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-II within Kaliganj Block (Phase-A). | SM/07002 | Retrofitting | PREPERATION OF DETAILS PROJECT FOR FHTC AT SURFACE WATER BASED W/S SCHEME ( N.SECTOR) , PART-II, ZONE-I, PHASE-A & B UNDER , NADIA DIVISION , PHE ,DTE |  |  | VCH/000306/2021-2022 | 139/FHTC | 17/08/2021 | 17/08/2021 | LEMNISCATE | 0.46 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-II within Kaliganj Block (Phase-A). | SM/07002 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT NORTHERN SECTOR PART-1 Z-2 |  |  | VCH/001080/2020-2021 | 445/DW | 25/03/2021 | 25/03/2021 | MONDAL ENTERPRISE | 44.33 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-II within Kaliganj Block (Phase-A). | SM/07002 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PIPE G.I/PVC PIPE OF AVERAGE LENGTH OF 10MM DIA GUN-METAL FERRULE, SADDLE PIECE 15MM DIA BIB COCK ETC AT SUBERNA BIHAR W/S SCHEME PART-B |  |  | VCH/000963/2021-2022 | 473/DW | 07/02/2022 | 07/02/2022 | ROY CONSTRUCTION | 0.73 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-II within Kaliganj Block (Phase-A). | SM/07002 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-II within Kaliganj block(Phase-A) in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000183/2020-2021 | 3589/ND | 08/12/2020 | 08/03/2021 | MONDAL ENTERPRISE | 97.01 | 90.15 | 92.93 | 0
5 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-II within Kaliganj Block (Phase-A). | SM/07002 | Retrofitting | Hiring of Diesel Ambassador Car/maxi cab for the office of the Assistant Engineer, Debagram Sub-Division, P.H. Engineering Dte., Debagram, Nadia with effect from 01/08/22 to 31/07/23 | Assistant Engineer |  | ORD/000186/2022-2023 | 312/D/DSD | 29/07/2022 | 29/07/2023 | TARUN KUMAR BHATTACHARYA | 4.8 | 1.11 | 23.21 | 70
Total | [13 empty] | 147.34 | 91.27 | 61.95