## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-VII within Kaliganj Block (Phase-A). | SM/07003 | Retrofitting | PROVIDING HOUSE CONNECTION INCLUDING SUPPLY OF 15MM DIA GI/PVC PIPE OF AVERAGE LENGTH OF 10MM DIA CUM GUN-METAL FERRULE, SADDLE PIECE 15MM AT KALIGANJ BLOCK |  |  | VCH/000788/2020-2021 | 382/DW | 04/02/2021 | 04/02/2021 | PROJECT INDIA | 78.41 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-VII within Kaliganj Block (Phase-A). | SM/07003 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-VII within Kaliganj block(Phase-A) in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000186/2020-2021 | 3592/ND | 08/12/2020 | 08/03/2021 | PROJECT INDIA | 96.53 | 18.12 | 18.78 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-VII within Kaliganj Block (Phase-A). | SM/07003 | Retrofitting | Hiring Diesel Luxury Car on daily basis (for 12 months from 01.02.2021 to 31.01.2022) for the office use of the Assistant Engineer, Kalyani Sub Division II, P.H.E. Dte | Assistant Engineer |  | ORD/000463/2020-2021 | 198 / KLYSD -II | 29/01/2021 | 29/01/2022 | SUMAN CHAKRABORTY | 4.8 | 0 | 0 | 0
Total | [13 empty] | 179.74 | 18.12 | 10.08