## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase- A) | SM/07417 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase- A) |  |  | VCH/000522/2021-2022 | 183/PFMS | 15/09/2021 | 15/09/2021 | NEERMAN | 86.15 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase- A) | SM/07417 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase- A) |  |  | VCH/000930/2021-2022 | 484/PFMS | 03/02/2022 | 03/02/2022 | LEMNISCATE | 0.72 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase- A) | SM/07417 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-IX, within Kaliganj Block (Phase-A, Retrofitting)" | Assistant Engineer | Junior Engineer 2 | ORD/000268/2020-2021 | 165/ND | 13/01/2021 | 13/04/2021 | NEERMAN | 95.28 | 1.77 | 1.86 | 0
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase- A) | SM/07417 | Retrofitting | Hiring of Diesel Ambassador Car/maxi cab for the office of the Assistant Engineer, Debagram Sub-Diovision,PHE Dte,Debagram,Nadia with effect from 01.08.2021 to 31.07.2022 | Assistant Engineer |  | ORD/000952/2021-2022 | 399/DSD | 29/07/2021 | 29/07/2022 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase- A) | SM/07417 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-IX within Kaliganj Block (Phase-B) | Assistant Engineer | Junior Engineer 2 | ORD/000090/2021-2022 | 2767/ND | 14/07/2021 | 12/10/2021 | M/S K.P. CONSTRUCTION | 91.11 | 0 | 0 | 0
Total | [13 empty] | 278.06 | 1.77 | 0.64