## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block [Phase-A] | SM/07418 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME ATPART-1 Z-8 |  |  | VCH/001069/2020-2021 | 460/DW | 30/03/2021 | 30/03/2021 | OTHERS | 80.19 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block [Phase-A] | SM/07418 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block [Phase-A] |  |  | VCH/000931/2021-2022 | 485/PFMS | 03/02/2022 | 03/02/2022 | LEMNISCATE | 0.48 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block [Phase-A] | SM/07418 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block ( Phase -A) | Assistant Engineer | Junior Engineer 2 | ORD/000200/2020-2021 | 4089ND | 31/12/2020 | 31/03/2021 | UMWELT ENGINEERS PVT LTD | 96.87 | 7.3 | 7.54 | 0
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block [Phase-A] | SM/07418 | Retrofitting | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Executive Engineer, Nadia Division, PHE Dte. (Period- 01/04/2023 to 30/09/2023) | Assistant Engineer |  | ORD/000548/2022-2023 | 465/ Kly SD-1 | 31/03/2023 | 30/09/2023 | ARROWTOWN DEALERS PVT. LTD | 2.4 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block [Phase-A] | SM/07418 | Retrofitting | Hiring of Diesel Ambassador Car/maxi cab for the office of the Assistant Engineer, Debagram Sub-Diovision,PHE Dte,Debagram,Nadia with effect from 01.08.2021 to 31.07.2022 | Assistant Engineer |  | ORD/000952/2021-2022 | 399/DSD | 29/07/2021 | 29/07/2022 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0 | 0
Total | [13 empty] | 184.74 | 7.3 | 3.95