## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Utter Tajpur W/S Scheme (Phase-I) of Retrofitting under Jal Swapno Programme | SM/07421 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT UTTAR TAJPUR |  |  | VCH/001064/2020-2021 | 459/DW | 30/03/2021 | 30/03/2021 | SARKAR AGENCY | 42.99 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Utter Tajpur W/S Scheme (Phase-I) of Retrofitting under Jal Swapno Programme | SM/07421 | Retrofitting | Providing Functional Household Tap Connection from Utter Tajpur W/S Scheme (Phase-I) of Retrofitting under Jal Swapno Programme |  |  | VCH/000472/2021-2022 | 268/PFMS | 08/10/2021 | 08/10/2021 | LEMNISCATE | 16.36 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Utter Tajpur W/S Scheme (Phase-I) of Retrofitting under Jal Swapno Programme | SM/07421 | Retrofitting | Continuation for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. | Assistant Engineer |  | ORD/000541/2022-2023 | 470/Kly SD-1 | 31/03/2023 | 30/06/2023 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 4.89 | 0 | 0 | 20
4 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Utter Tajpur W/S Scheme (Phase-I) of Retrofitting under Jal Swapno Programme | SM/07421 | Retrofitting | Hiring of Diesel Ambassador Car/maxi cab for the office of the Assistant Engineer, Debagram Sub-Diovision,PHE Dte,Debagram,Nadia with effect from 01.08.2021 to 31.07.2022 | Assistant Engineer |  | ORD/000952/2021-2022 | 399/DSD | 29/07/2021 | 29/07/2022 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Utter Tajpur W/S Scheme (Phase-I) of Retrofitting under Jal Swapno Programme | SM/07421 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Uttar Tajpur W/S scheme (Phase-I) of Rectrofitting in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000242/2020-2021 | 60/ND | 07/01/2021 | 07/04/2021 | SARKAR AGENCY | 96.79 | 27.02 | 27.91 | 100
Total | [13 empty] | 165.82 | 27.02 | 16.29