## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VII within Kaliganj Block (Phase-B) | SM/07429 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT PART-1 Z-VII |  |  | VCH/001062/2020-2021 | 459/DW | 30/03/2021 | 30/03/2021 | M/S DIPAK ENTERPRISE | 64.73 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VII within Kaliganj Block (Phase-B) | SM/07429 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-VII, within Kaliganj Block (Phase-B, Retrofitting)" | Assistant Engineer | Junior Engineer 2 | ORD/000266/2020-2021 | 163/ND | 13/01/2021 | 13/04/2021 | M/S DIPAK ENTERPRISE | 97.11 | 58.4 | 60.14 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VII within Kaliganj Block (Phase-B) | SM/07429 | Retrofitting | Laying of pipeline from Mira Bazar Baroari temple to traffic more under Mira - I G.P under Zone -VII of Surface Water Based Water Supply Scheme (Northern Sector), Part-I, within Kaliganj Block under Debagram Sub Division, P.H.Engineering Dte.(S.I. No -03.) | Assistant Engineer |  | ORD/000609/2021-2022 | 585/DSD | 31/12/2021 | 30/01/2022 | AVINABA ENGINEERING CONCERN | 0.64 | 0.6 | 92.73 | 0
Total | [13 empty] | 162.48 | 59 | 36.31