## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II, Nabadwip (Part) Block (Phase-D) | SM/07432 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II, Nabadwip (Part) Block (Phase-D) |  |  | VCH/000519/2021-2022 | 180/PFMS | 15/09/2021 | 15/09/2021 | MAHAVIR PUMPS MFG PVT. LTD. | 79.37 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II, Nabadwip (Part) Block (Phase-D) | SM/07432 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II, Nabadwip (Part) Block (Phase-D) |  |  | VCH/001009/2020-2021 |  | 25/03/2021 | 25/03/2021 | MAHABIR PUMPS MFG PVT. LTD. | 11.54 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II, Nabadwip (Part) Block (Phase-D) | SM/07432 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-IV, within Krishnagar-II & Nabadwip Block (Phase-D, Retrofitting)" | Assistant Engineer |  | ORD/000403/2020-2021 | 779/ND | 10/02/2021 | 11/05/2021 | MAHABIR PUMPS MFG PVT. LTD. | 97.11 | 23.08 | 23.77 | 0
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II, Nabadwip (Part) Block (Phase-D) | SM/07432 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000166/2023-2024 | 301/ND | 15/01/2024 | 15/01/2024 | Resource Division | 2.48 | 0 | 0 | 0
Total | [13 empty] | 190.51 | 23.08 | 12.12